## Issued Work Order (KALIMPONG)
Issued Work Order (KALIMPONG)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date
1 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | SM/15463 |  | New | SVS | 2660/NKWSMD | THUPDEN BHUTIA | 28-02-2023 | 26-10-2023
2 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | SM/18322 |  | New | SVS | 722/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 18-07-2023 | 17-07-2024
3 | KALIMPONG | PANKHASARI KHASMAHAL PWSS | SM/14170 |  | New | SVS | 2470/NKWSMD | THUPDEN BHUTIA | 06-02-2023 | 06-02-2024
4 | KALIMPONG | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 |  | New | MVS | 927/NKWSMD | GREEN VALLEY CONSTRUCTION | 12-07-2022 | 08-01-2023
5 | KALIMPONG | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11377 |  | New | SVS | 949/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 12-07-2022 | 10-10-2022
6 | KALIMPONG | TODAY TANGTA KHASMAHAL PWSS | SM/14171 |  | New | SVS | 2361/NKWSMD | MAHADEO PRASAD AGARWAL & CO | 01-02-2023 | 01-02-2024
7 | KALIMPONG | TODAY TANGTA KHASMAHAL PWSS | SM/14171 |  | New | SVS | 102/NKWSMD | MAHADEO PRASAD AGARWAL & CO | 28-04-2023 | 27-04-2024
8 | KALIMPONG | TODAY TANGTA KHASMAHAL PWSS | SM/14171 |  | New | SVS | 2353/NKWSMD | TASHI BHUTIA | 01-02-2023 | 01-02-2024
9 | KALIMPONG | TODAY TANGTA KHASMAHAL PWSS | SM/14171 |  | New | SVS | 2354/NKWSMD | TASHI BHUTIA | 01-02-2023 | 01-02-2024
10 | KALIMPONG | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/13610 |  | New | SVS | 2151/NKWSMD | M/S R.S. CONSTRUCTION | 20-01-2023 | 19-07-2023
11 | KALIMPONG | BINDU PIPED WATER SUPPLY SCHEME | SM/13622 |  | New | SVS | 2153/NKWSMD | JOJO CONSTUCTION | 20-01-2023 | 19-07-2023
12 | KALIMPONG | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 |  | New | MVS | 590/NKWSMD | SRINIWAS AGARWAL | 26-05-2022 | 22-11-2022
13 | KALIMPONG | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11955 |  | New | SVS | 1652/NKWSMD | BASANT PRADHAN | 04-11-2022 | 03-05-2023
14 | KALIMPONG | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11579 |  | New | SVS | 1497/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 14-10-2022 | 12-04-2023
15 | KALIMPONG | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/15646 |  | New | SVS | 2662/NKWSMD | SRINIWAS AGARWAL | 28-02-2023 | 26-10-2023
16 | KALIMPONG | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 |  | New | SVS | 1444/NKWSMD | D AND B GRACE | 28-09-2022 | 27-12-2022
17 | KALIMPONG | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11578 |  | New | SVS | 1496/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 14-10-2022 | 12-04-2023
18 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | SM/14192 |  | New | SVS | 2735/NKWSMD | ALLIED INSTRUMENTS | 03-03-2023 | 02-03-2024
19 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | SM/14193 |  | New | SVS | 359/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 26-05-2023 | 25-05-2024
20 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | SM/14194 |  | New | SVS | 672/NKWSMD | SRINIWAS AGARWAL | 12-07-2023 | 11-07-2024
21 | KALIMPONG | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | SM/13606 |  | New | SVS | 826/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 24-07-2023 | 20-03-2024
22 | KALIMPONG | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 |  | New | SVS | 1876/NKWSMD | SRINIWAS AGARWAL | 14-12-2022 | 10-10-2023
23 | KALIMPONG | GODAK BUSTY PIPED WATER SUPPLY SCHEME. | SM/13608 |  | New | SVS | 825/NKWSMD | SANJAY BHUJEL | 24-07-2023 | 20-03-2024
24 | KALIMPONG | GORUBATHAN-I PWSS | SM/14172 |  | New | MVS | 716/NKWSMD | M/S R.S. CONSTRUCTION | 18-07-2023 | 17-07-2024
25 | KALIMPONG | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 |  | New | SVS | 181/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 04-05-2023 | 03-05-2024
26 | KALIMPONG | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16233 |  | New | SVS | 673/NKWSMD | EVERSHINE CONSTRUCTION | 12-07-2023 | 11-07-2024
27 | KALIMPONG | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16649 |  | New | SVS | 105/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 28-04-2023 | 24-12-2023
28 | KALIMPONG | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | SM/10575 |  | New | SVS | 574/NKWSMD | HEMANT MOKTAN | 26-05-2022 | 24-08-2022
29 | KALIMPONG | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | SM/10562 |  | New | MVS | 501/NKWSMD | TIKARAM SHARMA | 24-05-2022 | 20-11-2022
30 | KALIMPONG | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10599 |  | New | SVS | 569/NKWSMD | SITA SHARMA | 26-05-2022 | 24-08-2022
31 | KALIMPONG | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10601 |  | New | SVS | 577/NKWSMD | SONAM TOPGAY BHUTIA | 26-05-2022 | 25-06-2022
32 | KALIMPONG | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10601 |  | New | SVS | 579/NKWSMD | SONAM TOPGAY BHUTIA | 26-05-2022 | 25-06-2022
33 | KALIMPONG | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10624 |  | New | SVS | 533/NKWSMD | SAINATH CONSTRUCTION COMPANY | 25-05-2022 | 23-08-2022
34 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | SM/16235 |  | New | SVS | 678/NKWSMD | NEOCON CONSTRUCTION CO | 12-07-2023 | 08-01-2024
35 | KALIMPONG | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | SM/10623 |  | New | SVS | 502/NKWSMD | BHUTIA AND SONS | 25-05-2022 | 23-08-2022
36 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/15042 |  | New | SVS | 2489/NKWSMD | THUPDEN BHUTIA | 09-02-2023 | 07-10-2023
37 | KALIMPONG | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10739 |  | New | SVS | 576/NKWSMD | DORJEE SHERPA | 26-05-2022 | 25-06-2022
38 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16234 |  | New | SVS | 679/NKWSMD | DIPENDRA CHETTRI | 12-07-2023 | 09-11-2023
39 | KALIMPONG | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10603 |  | New | SVS | 568/NKWSMD | PRAKASH TAMANG | 26-05-2022 | 24-08-2022
40 | KALIMPONG | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10625 |  | New | SVS | 573/NKWSMD | JUSTINE BHUTIA | 26-05-2022 | 24-08-2022
41 | KALIMPONG | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10576 |  | New | SVS | 571/NKWSMD | SACHIN RAI | 26-05-2022 | 24-08-2022
42 | KALIMPONG | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10563 |  | New | SVS | 575/NKWSMD | SANTOSH TAMANG | 26-05-2022 | 24-08-2022
43 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | SM/16513 |  | New | SVS | 97/NKWSMD | SANTOSH TAMANG | 28-04-2023 | 24-12-2023
44 | KALIMPONG | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | SM/10602 |  | New | SVS | 570/NKWSMD | DAWA TANGEE SHERPA | 26-05-2022 | 24-08-2022
45 | KALIMPONG | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | SM/10600 |  | New | SVS | 572/NKWSMD | SONAM TSHERING LEPCHA | 26-05-2022 | 24-08-2022
46 | KALIMPONG | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16512 |  | New | SVS | 96/NKWSMD | PASANG LAMA | 28-04-2023 | 26-08-2023
47 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT | SM/12180 |  | New | SVS | 1528/NKWSMD | SRINIWAS AGARWAL | 18-10-2022 | 15-06-2023
48 | KALIMPONG | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | SM/12181 |  | New | SVS | 1621/NKWSMD | SRINIWAS AGARWAL | 03-11-2022 | 03-11-2023
49 | KALIMPONG | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16231 |  | New | SVS | 360/NKWSMD | RAMESH KUMAR AGARWAL & CO | 26-05-2023 | 25-05-2024
50 | KALIMPONG | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16230 |  | New | SVS | 363/NKWSMD | YAMA CONSTRUCTIONS LLP | 29-05-2023 | 28-05-2024
51 | KALIMPONG | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 |  | New | MVS | 2731/NKWSMD | PUSHPA KUMAR RIZAL | 03-03-2023 | 30-08-2023
52 | KALIMPONG | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 |  | New | SVS | 416/NKWSMD | SACHIN RAI | 05-06-2023 | 31-01-2024
53 | KALIMPONG | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | SM/15937 |  | New | MVS | 2732/NKWSMD | RAMESH KUMAR AGARWAL & CO | 03-03-2023 | 02-03-2024
54 | KALIMPONG | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG | SM/16511 |  | New | SVS | 412/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 05-06-2023 | 04-06-2024
55 | KALIMPONG | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | SM/13603 |  | New | SVS | 2352/NKWSMD | DIL KUMAR RAI | 01-02-2023 | 01-02-2024
56 | KALIMPONG | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 |  | New | SVS | 2147/NKWSMD | SANTOSH TAMANG | 20-01-2023 | 19-07-2023
57 | KALIMPONG | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | SM/11806 |  | New | MVS | 1155/NKWSMD | JUSTINE BHUTIA | 12-08-2022 | 08-02-2023
58 | KALIMPONG | NEORAKHOLA WATER SUPPLY SCHEME | SM/00896 |  |  | MVS | 107/NKWSMD | DHURBA KUMAR PRADHAN | 13-04-2022 | 10-10-2022
59 | KALIMPONG | NEORAKHOLA WATER SUPPLY SCHEME | SM/00896 | SM/08693 | Retrofitting | MVS | 167/NKWSMD | SONAM TOPGAY BHUTIA | 06-09-2021 | 06-10-2021
60 | KALIMPONG | NEORAKHOLA WATER SUPPLY SCHEME | SM/00896 | SM/08693 | Retrofitting | MVS | 166/NKWSMD | SONAM TOPGAY BHUTIA | 06-09-2021 | 06-10-2021
61 | KALIMPONG | NEORAKHOLA WATER SUPPLY SCHEME | SM/00896 | SM/10512 | Retrofitting | MVS | 139/NKWSMD | SONAM TOPGAY BHUTIA | 20-04-2022 | 17-10-2022
62 | KALIMPONG | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | SM/18415 |  | New | MVS | 945/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 17-08-2023 | 16-08-2024
63 | KALIMPONG | PAGRAN BONG KHASMAHAL PWSS | SM/16854 |  | New | SVS | 684/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 12-07-2023 | 08-03-2024
64 | KALIMPONG | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 |  | New | SVS | 711/NKWSMD | SILAN GURUNG | 17-07-2023 | 13-01-2024
65 | KALIMPONG | PATEN GODAK KHASMAHAL PWSS | SM/18255 |  | New | SVS | 710/NKWSMD | THUPDEN BHUTIA | 17-07-2023 | 16-07-2024
66 | KALIMPONG | Piped Water Supply Scheme for Pedong Bazar & Adj. Mouzas | SM/03623 | SM/07872 | Retrofitting | MVS | 297/NKWSMD | LEGDEN PRADHAN | 25-01-2021 | 26-03-2021
67 | KALIMPONG | Piped Water Supply Scheme for Pedong Bazar & Adj. Mouzas | SM/03623 | SM/07872 | Retrofitting | MVS | 187/NKWSMD | LEGDEN PRADHAN | 12-10-2020 | 11-12-2020
68 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10703 |  | New | SVS | 589/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 26-05-2022 | 22-03-2023
69 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10704 |  | New | SVS | 1112/NKWSMD | SUNNY CONSTRUCTION | 05-08-2022 | 01-06-2023
70 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10699 |  | New | SVS | 528/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 25-05-2022 | 21-11-2022
71 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10698 |  | New | SVS | 527/NKWSMD | SRINIWAS AGARWAL | 25-05-2022 | 21-11-2022
72 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10702 |  | New | SVS | 291/NKWSMD | PEMA BHUTIA | 13-05-2022 | 09-11-2022
73 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10697 |  | New | SVS | 1096/NKWSMD | BRISTI CONSTRUCTION | 01-08-2022 | 28-01-2023
74 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10700 |  | New | SVS | 491/NKWSMD | SRINIWAS AGARWAL | 24-05-2022 | 20-11-2022
75 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10696 |  | New | SVS | 526/NKWSMD | MAHADEO PRASAD AGARWAL & CO | 25-05-2022 | 21-11-2022
76 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI,RAI, DHAJEY GOAN. | SM/09544 |  | New | SVS | 448/NKWSMD | SUNIL BAJLA | 14-01-2022 | 14-04-2022
77 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO KASHYONE. | SM/09599 |  | New | SVS | 627/NKWSMD | DINESH SHERPA | 21-02-2022 | 21-07-2022
78 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10695 |  | New | SVS | 553/NKWSMD | PASANG LAMA & SONS(HUF) | 26-05-2022 | 22-11-2022
79 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10694 |  | New | SVS | 522/NKWSMD | SRINIWAS AGARWAL | 25-05-2022 | 24-07-2022
80 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10701 |  | New | SVS | 832/NKWSMD | SANGAM GURUNG | 30-06-2022 | 27-12-2022
81 | KALIMPONG | PIPED WATER SUPPLY SCHEME FROM SISNEY JHORA TO NORTH PEDONG | SM/09665 |  | New | SVS | 450/NKWSMD | GETEN NAMGYAL BHUTIA | 14-01-2022 | 14-04-2022
82 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 260/NKWSMD | SUNNY CONSTRUCTION | 20-02-2024 | 18-08-2024
83 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 257/NKWSMD | KHALING ENTERPRISES | 20-02-2024 | 18-08-2024
84 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 262/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 20-02-2024 | 18-08-2024
85 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 258/NKWSMD | SANTOSH TAMANG | 20-02-2024 | 18-08-2024
86 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 256/NKWSMD | DINESH SHERPA | 20-02-2024 | 19-02-2025
87 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 261/NKWSMD | SANTOSH TAMANG | 20-02-2024 | 18-08-2024
88 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 259/NKWSMD | DIPESH RAI | 20-02-2024 | 18-08-2024
89 | KALIMPONG | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/19176 |  | New | SVS | 255/NKWSMD | SUNNY CONSTRUCTION | 20-02-2024 | 18-08-2024
90 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15641 |  | New | SVS | 2668/NKWSMD | DIPESH RAI | 28-02-2023 | 27-08-2023
91 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13615 |  | New | SVS | 2350/NKWSMD | BHUTIA AND SONS | 01-02-2023 | 02-05-2023
92 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/16514 |  | New | SVS | 417/NKWSMD | THUPDEN BHUTIA | 05-06-2023 | 04-06-2024
93 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/16232 |  | New | SVS | 414/NKWSMD | EVERSHINE CONSTRUCTION | 05-06-2023 | 31-01-2024
94 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13617 |  | New | SVS | 1874/NKWSMD | YAMA CONSTRUCTIONS LLP | 14-12-2022 | 11-08-2023
95 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13616 |  | New | SVS | 2149/NKWSMD | THUPDEN BHUTIA | 20-01-2023 | 19-07-2023
96 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15642 |  | New | SVS | 2652/NKWSMD | KAMAKHAYA CONSTRUCTION | 28-02-2023 | 26-10-2023
97 | KALIMPONG | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 |  | New | SVS | 2005/NKWSMD | SANTOSH TAMANG | 23-12-2022 | 21-06-2023
98 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/18247 |  | New | SVS | 717/NKWSMD | SRINIWAS AGARWAL | 18-07-2023 | 17-07-2024
99 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15645 |  | New | SVS | 220/NKWSMD | SRINIWAS AGARWAL | 10-05-2023 | 09-05-2024
100 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | SM/15644 |  | New | SVS | 222/NKWSMD | SITA SHARMA | 10-05-2023 | 09-05-2024
101 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12630 |  | New | SVS | 1450/NKWSMD | GARGO TRADERS | 29-09-2022 | 26-07-2023
102 | KALIMPONG | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12629 |  | New | SVS | 1448/NKWSMD | SRINIWAS AGARWAL | 29-09-2022 | 26-07-2023
103 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | SM/15643 |  | New | SVS | 2653/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-02-2023 | 27-08-2023
104 | KALIMPONG | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/15640 |  | New | SVS | 2659/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 28-02-2023 | 26-10-2023
105 | KALIMPONG | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10791 |  | New | SVS | 816/NKWSMD | GARGO TRADERS | 30-06-2022 | 26-04-2023
106 | KALIMPONG | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | SM/10787 |  | New | SVS | 961/NKWSMD | M/S KAMAK ENGINEERS AND CO. | 12-07-2022 | 08-05-2023
107 | KALIMPONG | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 |  | New | SVS | 963/NKWSMD | SRINIWAS AGARWAL | 12-07-2022 | 08-05-2023
108 | KALIMPONG | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10792 |  | New | SVS | 960/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 12-07-2022 | 08-05-2023
109 | KALIMPONG | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10635 |  | New | SVS | 830/NKWSMD | SANTOSH TAMANG | 30-06-2022 | 27-12-2022
110 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 823/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 24-07-2023 | 20-03-2024
111 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 119/NKWSMD | SANTOSH TAMANG | 16-01-2024 | 15-01-2025
112 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 821/NKWSMD | NIM TSHERING LEPCHA | 24-07-2023 | 21-11-2023
113 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 819/NKWSMD | PRAKASH TAMANG | 24-07-2023 | 21-11-2023
114 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 1091/NKWSMD | SANTOSH TAMANG | 21-09-2023 | 19-01-2024
115 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 972/NKWSMD | EVERSHINE CONSTRUCTION | 18-06-2024 | 15-12-2024
116 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 973/NKWSMD | KAMAKHYA CONSTRUCTION | 18-06-2024 | 15-12-2024
117 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 817/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 24-07-2023 | 20-03-2024
118 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 1308/NKWSMD | BINOD CHANDRA BHUJEL | 31-10-2023 | 30-12-2023
119 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 1307/NKWSMD | D AND B GRACE | 31-10-2023 | 29-01-2024
120 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 822/NKWSMD | JUSTINE BHUTIA | 24-07-2023 | 20-03-2024
121 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 818/NKWSMD | SITA SHARMA | 24-07-2023 | 21-11-2023
122 | KALIMPONG | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | SM/18443 |  | New | MVS | 824/NKWSMD | JUSTINE BHUTIA | 24-07-2023 | 21-11-2023
123 | KALIMPONG | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | SM/11312 |  | New | SVS | 815/NKWSMD | DIPENDRA CHETTRI | 30-06-2022 | 28-09-2022
124 | KALIMPONG | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | SM/11312 |  | New | SVS | 815/NKWSMD | DIPENDRA CHETTRI | 30-06-2022 | 28-09-2022
125 | KALIMPONG | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 |  | New | MVS | 626/NKWSMD | GARGO TRADERS | 21-02-2022 | 21-07-2022
126 | KALIMPONG | PWS SCHEM FROM OKHERBOTEY KHOLA TO UPPER PEDONG | SM/09547 |  | New | SVS | 445/NKWSMD | GETEN NAMGYAL BHUTIA | 14-01-2022 | 14-04-2022
127 | KALIMPONG | PWS SCHEME BHERI POSHYER KHOLA TO KOTHI LINE | SM/09606 |  | New | SVS | 427/NKWSMD | M/S R.S. CONSTRUCTION | 07-01-2022 | 07-04-2022
128 | KALIMPONG | Pws scheme from 7th Mile Jhora to Algarah | SM/09602 |  | New | SVS | 622/NKWSMD | JUSTINE BHUTIA | 21-02-2022 | 21-07-2022
129 | KALIMPONG | PWS SCHEME FROM 9TH MILE JHORA TO 18TH MILE | SM/09603 |  | New | SVS | 629/NKWSMD | SUNIL BAJLA | 21-02-2022 | 21-07-2022
130 | KALIMPONG | PWS SCHEME FROM AMBIOK KHOLA (PARBALAKHA) TO GORUBATHAN TAR | SM/09608 |  | New | SVS | 624/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 21-02-2022 | 21-07-2022
131 | KALIMPONG | PWS SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON | SM/09668 |  | New | SVS | 455/NKWSMD | SAMSHER RAI | 14-01-2022 | 14-04-2022
132 | KALIMPONG | PWS SCHEME FROM BANGLA JHORA TO JOGITAR | SM/10750 |  | New | SVS | 523/NKWSMD | M/S R.S. CONSTRUCTION | 25-05-2022 | 24-07-2022
133 | KALIMPONG | PWS SCHEME FROM BARA SUKAY KHOLA TO CHOTTA MANZING | SM/09540 |  | New | MVS | 446/NKWSMD | PRAKASH TAMANG | 14-01-2022 | 14-04-2022
134 | KALIMPONG | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK | SM/10747 |  | New | SVS | 834/NKWSMD | ANAND KUMAR LAKHOTIA | 30-06-2022 | 29-08-2022
135 | KALIMPONG | PWS SCHEME FROM BHUPALEY KHOLA TO PAREN | SM/09607 |  | New | SVS | 453/NKWSMD | RAMESH KUMAR AGARWAL & CO | 14-01-2022 | 14-04-2022
136 | KALIMPONG | PWS SCHEME FROM BICHRI DHARA TO LOWER SUNGDUNG | SM/09611 |  | New | SVS | 422/NKWSMD | SUNNY CONSTRUCTION | 07-01-2022 | 07-04-2022
137 | KALIMPONG | PWS SCHEME FROM CHAGEY KHOLA TO KATAREY GAON | SM/09615 |  | New | SVS | 451/NKWSMD | NIM TSHERING LEPCHA | 14-01-2022 | 14-04-2022
138 | KALIMPONG | PWS SCHEME FROM CHAGEY KHOLA TO SAURENI | SM/09664 |  | New | SVS | 421/NKWSMD | THUPDEN BHUTIA | 07-01-2022 | 07-04-2022
139 | KALIMPONG | PWS SCHEME FROM CHAMUNG KHOLA TO GITDABLING BAZAR | SM/09601 |  | New | SVS | 429/NKWSMD | SITA SHARMA | 07-01-2022 | 07-04-2022
140 | KALIMPONG | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY | SM/09543 |  | New | SVS | 628/NKWSMD | SRINIWAS AGARWAL | 21-02-2022 | 21-07-2022
141 | KALIMPONG | PWS SCHEME FROM CHAWA KHOLA TO RELLI | SM/09610 |  | New | SVS | 424/NKWSMD | DIPESH RAI | 07-01-2022 | 07-04-2022
142 | KALIMPONG | PWS SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON | SM/09542 |  | New | SVS | 889/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-03-2022 | 26-06-2022
143 | KALIMPONG | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | SM/10741 |  | New | SVS | 591/NKWSMD | MAHADEO PRASAD AGARWAL & CO | 26-05-2022 | 25-07-2022
144 | KALIMPONG | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG | SM/11342 |  | New | SVS | 808/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 30-06-2022 | 29-08-2022
145 | KALIMPONG | PWS SCHEME FROM DEORALI KHOLA TO PAKANG | SM/11341 |  | New | SVS | 788/NKWSMD | TIKARAM SHARMA | 30-06-2022 | 27-12-2022
146 | KALIMPONG | PWS SCHEME FROM DHATURAY JHORA TO DEWARLI GAON, GUMBA GAON, BICH GAON | SM/09596 |  | New | SVS | 625/NKWSMD | SANTOSH TAMANG | 21-02-2022 | 21-07-2022
147 | KALIMPONG | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP | SM/10755 |  | New | SVS | 534/NKWSMD | GETEN NAMGYAL BHUTIA | 25-05-2022 | 21-11-2022
148 | KALIMPONG | PWS SCHEME FROM GAIRIBAS KHOLA& GEET KHOLA TO JHANDI | SM/09541 |  | New | MVS | 9/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 04-04-2022 | 01-10-2022
149 | KALIMPONG | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | SM/11354 |  | New | SVS | 1357/NKWSMD | DINESH SHERPA | 21-09-2022 | 19-01-2023
150 | KALIMPONG | PWS SCHEME FROM HARI KHOLA TO UPPER LOWER GUMTI | SM/09539 |  | New | SVS | 456/NKWSMD | SUBAN RAI | 14-01-2022 | 14-04-2022
151 | KALIMPONG | PWS SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA | SM/09597 |  | New | SVS | 454/NKWSMD | SANTOSH TAMANG | 14-01-2022 | 14-04-2022
152 | KALIMPONG | PWS SCHEME FROM JHOLUNG KHOLA TO 45 DHURA | SM/09584 |  | New | SVS | 427/NKWSMD | M/S R.S. CONSTRUCTION | 07-01-2022 | 07-04-2022
153 | KALIMPONG | PWS SCHEME FROM JHOLUNG KHOLA TO UPPER, LOWER AND MIDDLE DHAP | SM/09667 |  | New | SVS | 623/NKWSMD | RAMESH KUMAR AGARWAL & CO | 21-02-2022 | 21-07-2022
154 | KALIMPONG | PWS SCHEME FROM JHOLUNGAY KHOLA(BANDUKEY) TO DOKAN DARA | SM/09605 |  | New | SVS | 449/NKWSMD | MAHADEO PRASAD AGARWAL & CO | 14-01-2022 | 14-04-2022
155 | KALIMPONG | PWS SCHEME FROM KAIJARBOTEY JHORA TO LOWER POSHYER BHASMEY | SM/09614 |  | New | MVS | 452/NKWSMD | SUDEN TAMANG | 14-01-2022 | 14-04-2022
156 | KALIMPONG | PWS SCHEME FROM KAMZER KHOLA TO LOLAY DOKAN DARA | SM/09616 |  | New | SVS | 428/NKWSMD | DIPESH RAI | 07-01-2022 | 07-04-2022
157 | KALIMPONG | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY | SM/10754 |  | New | SVS | 552/NKWSMD | SHASHI LEPCHA | 26-05-2022 | 22-11-2022
158 | KALIMPONG | PWS SCHEME FROM KHANI KHOLA TO CHUKIM | SM/10753 |  | New | SVS | 529/NKWSMD | PASANG LAMA | 25-05-2022 | 21-11-2022
159 | KALIMPONG | PWS SCHEME FROM KHARKHOLA TO LOWER REON | SM/10756 |  | New | MVS | 536/NKWSMD | TIKARAM SHARMA | 25-05-2022 | 21-11-2022
160 | KALIMPONG | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE | SM/10749 |  | New | MVS | 503/NKWSMD | PRAYOG RAI | 25-05-2022 | 21-11-2022
161 | KALIMPONG | PWS SCHEME FROM MANDIR KHOLA TO TANYANG | SM/10751 |  | New | SVS | 551/NKWSMD | AMIT KUMAR THAPA | 26-05-2022 | 22-11-2022
162 | KALIMPONG | PWS SCHEME FROM MAWATAR TO UPPER DABLING | SM/09546 |  | New | SVS | 419/NKWSMD | TIKARAM SHARMA | 07-01-2022 | 07-04-2022
163 | KALIMPONG | PWS SCHEME FROM NIMBONG KHOLA TO SALDARA | SM/09670 |  | New | SVS | 420/NKWSMD | SANTOSH TAMANG | 07-01-2022 | 07-04-2022
164 | KALIMPONG | PWS SCHEME FROM OKHERBOTEY JHORA TO DARA GAON | SM/09598 |  | New | SVS | 426/NKWSMD | DINESH SHERPA | 07-01-2022 | 07-04-2022
165 | KALIMPONG | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN | SM/10745 |  | New | SVS | 616/NKWSMD | DIL KUMAR RAI | 26-05-2022 | 25-07-2022
166 | KALIMPONG | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION | SM/10744 |  | New | SVS | 531/NKWSMD | YAMA CONSTRUCTIONS LLP | 25-05-2022 | 21-11-2022
167 | KALIMPONG | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | SM/10746 |  | New | SVS | 532/NKWSMD | YAMA CONSTRUCTIONS LLP | 25-05-2022 | 21-11-2022
168 | KALIMPONG | PWS SCHEME FROM PHENTO SOURCE TO DUKA | SM/10748 |  | New | SVS | 535/NKWSMD | SUNIL BAJLA | 25-05-2022 | 21-11-2022
169 | KALIMPONG | PWS SCHEME FROM REON KHOLA TO LOWER PEMBLING | SM/09609 |  | New | SVS | 431/NKWSMD | SANTOSH TAMANG | 07-01-2022 | 07-04-2022
170 | KALIMPONG | PWS SCHEME FROM SAMTHARA KHOLA TO CENTRE GAON, PINTALAY GAON, GUDARA GAON, BICH GAON, CHETTRI GAON | SM/09612 |  | New | SVS | 749/NKWSMD | DINESH SHERPA | 28-02-2022 | 29-05-2022
171 | KALIMPONG | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY | SM/11340 |  | New | SVS | 790/NKWSMD | PRAKASH TAMANG | 30-06-2022 | 27-12-2022
172 | KALIMPONG | PWS SCHEME FROM SISNEY AND ANKUREY JHORA TO NOKDARA | SM/09600 |  | New | SVS | 458/NKWSMD | DIPESH RAI | 14-01-2022 | 14-04-2022
173 | KALIMPONG | PWS SCHEME FROM SISNEY JHORA TO SAMTHAR BAZAR | SM/10742 |  | New | SVS | 530/NKWSMD | YADI LEPCHA | 25-05-2022 | 21-11-2022
174 | KALIMPONG | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY | SM/10752 |  | New | SVS | 833/NKWSMD | RABIN RAI | 30-06-2022 | 29-08-2022
175 | KALIMPONG | PWS SCHEME FROM THAKALEY JHORA TO VATTY DARA 3RD MILE | SM/09666 |  | New | SVS | 430/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 07-01-2022 | 07-04-2022
176 | KALIMPONG | PWS SCHEME FROM THUKCHUK KHOLA TO 20TH MILE | SM/09594 |  | New | SVS | 10/NKWSMD | THUPDEN BHUTIA | 04-04-2022 | 01-10-2022
177 | KALIMPONG | PWS SCHEME FROM UNEAK KHOLA TO DABLING | SM/09595 |  | New | SVS | 425/NKWSMD | YAMA CONSTRUCTIONS LLP | 07-01-2022 | 07-04-2022
178 | KALIMPONG | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA | SM/10743 |  | New | SVS | 521/NKWSMD | ANAND MANI PRADHAN | 25-05-2022 | 24-07-2022
179 | KALIMPONG | PWSS FROM BHARKHOP JHORA TO LOWER KAFFER | SM/11343 |  | New | SVS | 809/NKWSMD | SANTOSH TAMANG | 30-06-2022 | 29-08-2022
180 | KALIMPONG | PWSS FROM MALI KHOLA TO KASHMI FOREST VILLAGE | SM/09617 |  | New | SVS | 457/NKWSMD | ANAND MANI PRADHAN | 14-01-2022 | 14-04-2022
181 | KALIMPONG | PWSS SCHEME FROM KHANI KHOLA TO WEST SAMALBONG | SM/09669 |  | New | SVS | 423/NKWSMD | BASANT PRADHAN | 07-01-2022 | 07-04-2022
182 | KALIMPONG | PWSS SCHEME FROM NIMBONG KHOLA TO UPPER AND LOWER GESHOK AND GAIRIGAON | SM/09545 |  | New | SVS | 432/NKWSMD | SANTOSH TAMANG | 07-01-2022 | 07-04-2022
183 | KALIMPONG | PWSS SCHEME FROM SISNEY KHOLA TO UPPER AND LOWER KAMBAL & DINGALI GAON | SM/09613 |  | New | SVS | 754/NKWSMD | MR. DAWA LAMA | 28-02-2022 | 29-05-2022
184 | KALIMPONG | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 |  | New | MVS | 2491/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 09-02-2023 | 09-02-2024
185 | KALIMPONG | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/13611 |  | New | SVS | 2493/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 09-02-2023 | 09-02-2024
186 | KALIMPONG | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 |  | New | SVS | 358/NKWSMD | THUPDEN BHUTIA | 26-05-2023 | 21-01-2024
187 | KALIMPONG | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | SM/14191 |  | New | SVS | 2492/NKWSMD | JUSTINE BHUTIA | 09-02-2023 | 09-02-2024
188 | KALIMPONG | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 |  | New | SVS | 962/NKWSMD | THUPDEN BHUTIA | 12-07-2022 | 08-05-2023
189 | KALIMPONG | SURUK PIPED WATER SUPPLY SCHEME | SM/13607 |  | New | SVS | 2490/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 09-02-2023 | 09-02-2024
190 | KALIMPONG | UPPER FAGU PIPED WATER SUPPLY SCHEME. | SM/13954 |  | New | MVS | 723/NKWSMD | M/S R.S. CONSTRUCTION | 18-07-2023 | 17-07-2024
191 | KALIMPONG | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | SM/18589 |  | New | SVS | 891/NKWSMD | SRINIWAS AGARWAL | 07-08-2023 | 06-08-2024