## Issued Work Order (PASCHIM BARD
Issued Work Order (PASCHIM BARDHAMAN)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date
1 | PASCHIM BARDHAMAN | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | SM/15639 | Augmentation | MVS | 1175/DWSD | RANADHIR SINHA | 02-08-2022 | 14-08-2022
2 | PASCHIM BARDHAMAN | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 |  | New | MVS | 1438/DWSD | HANNAN BUILDERS PVT. LTD. | 13-10-2022 | 25-10-2022
3 | PASCHIM BARDHAMAN | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | SM/07391 | Retrofitting | MVS | 789/DWSD | BISHAL ENTERPRISE | 18-05-2022 | 02-07-2022
4 | PASCHIM BARDHAMAN | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | SM/16903 | Augmentation | SVS | 1606/DWSD | BISHAL ENTERPRISE | 21-08-2023 | 19-11-2023
5 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 |  |  | MVS | 1159/DWSD | BISHAL ENTERPRISE | 28-10-2020 | 12-12-2020
6 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 | SM/07391 | Retrofitting | MVS | 138/DWSD | JOY GURU ENTERPRISE | 28-01-2021 | 27-02-2021
7 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 | SM/07391 | Retrofitting | MVS | 1707/DWSD | MD AAMIR KHAN | 08-12-2021 | 07-01-2022
8 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 |  |  | MVS | 1376/DWSD | M/S S. CHOUDHURY | 17-09-2021 | 16-11-2021
9 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 | SM/07391 | Retrofitting | MVS | 1706/DWSD | MD AAMIR KHAN | 08-12-2021 | 07-01-2022
10 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 |  |  | MVS | 1440/DWSD | SUBHADEEP DAS | 28-12-2020 | 22-01-2021
11 | PASCHIM BARDHAMAN | Basudha Piped Water Supply Scheme | SM/05631 |  |  | MVS | 1321/DWSD | M/S S. CHOUDHURY | 09-12-2020 | 23-01-2021
12 | PASCHIM BARDHAMAN | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 |  | New | MVS | 1437/DWSD | KHAN ENTERPRISE | 13-10-2022 | 25-10-2022
13 | PASCHIM BARDHAMAN | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | SM/07391 | Retrofitting | MVS | 150/DWSD | SK. ALIM | 07-02-2022 | 09-03-2022
14 | PASCHIM BARDHAMAN | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | SM/07391 | Retrofitting | MVS | 149/DWSD | MACHINO TECHNO | 07-02-2022 | 13-04-2022
15 | PASCHIM BARDHAMAN | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | SM/07391 | Retrofitting | MVS | 148/DWSD | TARA CONSTRUCTION | 07-02-2022 | 09-03-2022
16 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 1147/RCD-I | GITASHREE FABRICATION | 22-07-2021 | 21-08-2021
17 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 956/RCD-I | SUMIT BANERJEE | 07-06-2021 | 07-07-2021
18 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 957/RCD-I | BABA LOKNATH ENTERPRISE | 07-06-2021 | 07-07-2021
19 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 958/RCD-I | KHEPI MAA TRADERS | 07-06-2021 | 07-07-2021
20 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 959/RCD-I | JAYANTA DATTA | 07-06-2021 | 07-07-2021
21 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07561 | Retrofitting | MVS | 963/RCD-I | DAS & CHAKRABORTY | 07-06-2021 | 07-07-2021
22 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 1148/RCD-I | GITA CONSTRUCTION | 22-07-2021 | 21-08-2021
23 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 953/RCD-I | TARA MA ENTERPRISE | 07-06-2021 | 07-07-2021
24 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 954/RCD-I | PINKI ENTERPRISE | 07-06-2021 | 07-07-2021
25 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 955/RCD-I | MD AAMIR KHAN | 07-06-2021 | 07-07-2021
26 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07561 | Retrofitting | MVS | 962/RCD-I | ASHA CONSTRUCTION | 07-06-2021 | 07-07-2021
27 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 960/RCD-I | M/S MONDAL ENTERPRISE | 07-06-2021 | 07-07-2021
28 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 952/RCD-I | DIP CONSTRUCTION | 07-06-2021 | 07-07-2021
29 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 961/RCD-I | S. CHAKRABORTY & CO. | 07-06-2021 | 07-07-2021
30 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 488/RCD I | SUBHADEEP DAS | 03-02-2023 | 05-03-2023
31 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 488/RCD I | SUBHADEEP DAS | 03-02-2023 | 05-03-2023
32 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 488/RCD I | SUBHADEEP DAS | 03-02-2023 | 05-03-2023
33 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 1262/ RCD I | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 27-03-2023 | 11-04-2023
34 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07561 | Retrofitting | MVS | 1262/ RCD I | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 27-03-2023 | 11-04-2023
35 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07559 | Retrofitting | MVS | 1980/RCD I | KHEPI MAA TRADERS | 24-08-2022 | 08-09-2022
36 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07560 | Retrofitting | MVS | 1980/RCD I | KHEPI MAA TRADERS | 24-08-2022 | 08-09-2022
37 | PASCHIM BARDHAMAN | Chotkara Kanskuli Piped Water Supply Scheme | SM/05165 | SM/07558 | Retrofitting | MVS | 1980/RCD I | KHEPI MAA TRADERS | 24-08-2022 | 08-09-2022
38 | PASCHIM BARDHAMAN | CHURULIA AND ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00756 | SM/11205 | Augmentation | MVS | 1372/RCD-I | ASHA CONSTRUCTION | 16-06-2022 | 13-12-2022
39 | PASCHIM BARDHAMAN | CHURULIA AND ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00756 | SM/11205 | Augmentation | MVS | 1276/RCD-I | MD AAMIR KHAN | 02-06-2022 | 31-08-2022
40 | PASCHIM BARDHAMAN | CHURULIA AND ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00756 | SM/11205 | Augmentation | MVS | 1762/RCD I | MD AAMIR KHAN | 16-05-2023 | 12-11-2023
41 | PASCHIM BARDHAMAN | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | SM/16901 | Augmentation | MVS | 1656/DWSD | SUPER SKILL | 05-12-2022 | 17-12-2022
42 | PASCHIM BARDHAMAN | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 |  | New | MVS | 1614/DWSD | POWER TOOLS AND ENGINEERING | 21-11-2022 | 03-12-2022
43 | PASCHIM BARDHAMAN | Dhandadihi Piped Water Supply Scheme | SM/04897 | SM/07392 | Retrofitting | MVS | 1032/RCD-I | MACHINO TECHNO | 05-11-2020 | 05-12-2020
44 | PASCHIM BARDHAMAN | DHOBARU PIPED WATER SUPPLY SCHEME | SM/10999 | SM/16902 | Augmentation | SVS | 1133/DWSD | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 20-07-2023 | 19-08-2023
45 | PASCHIM BARDHAMAN | DHOBARU PIPED WATER SUPPLY SCHEME | SM/10999 | SM/07391 | Retrofitting | MVS | 774/DWSD | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 17-05-2022 | 01-07-2022
46 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10605 | Augmentation | MVS | 1279/RCD I | M/S B.K. CONSTRUCTION | 02-06-2022 | 31-08-2022
47 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10643 | Augmentation | MVS | 3274/RCDI | M/S S.K. ENTERPRISE | 20-12-2022 | 19-01-2023
48 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10165 | Augmentation | MVS | 2468/RCDI | A. CONSTRUCTION CO. | 14-10-2022 | 28-11-2022
49 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10643 | Augmentation | MVS | 2519/RCDI | MAA ENTERPRISE | 20-10-2022 | 19-11-2022
50 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10605 | Augmentation | MVS | 1277/RCD-I | JAYANTA DATTA | 02-06-2022 | 31-08-2022
51 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10643 | Augmentation | MVS | 2520/RCDI | B.T.M CONCERN | 20-10-2022 | 19-11-2022
52 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10165 | Augmentation | MVS | 2015/RCD-I | GITA CONSTRUCTION | 26-08-2022 | 10-10-2022
53 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 |  |  | MVS | 1278/RCD-I | MD. JAWED KHAN | 02-06-2022 | 31-08-2022
54 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10605 | Augmentation | MVS | 1278/RCD-I | MD. JAWED KHAN | 02-06-2022 | 31-08-2022
55 | PASCHIM BARDHAMAN | EXTENSION OF JAMGRAM PANURIA (KHARABAR | SM/00759 | SM/10643 | Augmentation | MVS | 1053/RCD-I | SRI KRISHNA ENTERPRISE | 23-03-2023 | 22-04-2023
56 | PASCHIM BARDHAMAN | GARADAHA PIPED WATER SUPPLY SCHEME. | SM/11934 | SM/07391 | Retrofitting | MVS | 775/DWSD | SHWET BARANI | 17-05-2022 | 01-07-2022
57 | PASCHIM BARDHAMAN | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | SM/10998 |  | New | MVS | 764/DWSD | BABA LOKENATH ENTERPRISE | 13-05-2022 | 27-06-2022
58 | PASCHIM BARDHAMAN | GOPALPUR W/S SCHEME | SM/00733 | SM/09875 | Augmentation | SVS | 68/DWSD | MRITYUNJOY MUKHERJEE AND CO | 19-01-2022 | 18-07-2022
59 | PASCHIM BARDHAMAN | Gourbazar and adj. mouzas water supply scheme | SM/02986 | SM/09063 | Retrofitting | MVS | 1865/RCD-I | M/S S.K. ENTERPRISE | 28-10-2021 | 27-11-2021
60 | PASCHIM BARDHAMAN | Gourbazar and adj. mouzas water supply scheme | SM/02986 | SM/09063 | Retrofitting | MVS | 1866/RCD-I | VISUVIOUS | 28-10-2021 | 27-11-2021
61 | PASCHIM BARDHAMAN | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) | SM/13863 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
62 | PASCHIM BARDHAMAN | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) | SM/13863 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
63 | PASCHIM BARDHAMAN | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | SM/13866 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
64 | PASCHIM BARDHAMAN | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | SM/13866 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
65 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) | SM/13862 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
66 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) | SM/13862 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
67 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) | SM/13864 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
68 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) | SM/13864 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
69 | PASCHIM BARDHAMAN | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Maheshpur,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-A) | SM/13879 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
70 | PASCHIM BARDHAMAN | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) | SM/13861 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
71 | PASCHIM BARDHAMAN | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) | SM/13861 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
72 | PASCHIM BARDHAMAN | Ground water based mini piped water supply scheme (Max 100 House Hold) for Pathardiha,GP-Gopalpur,Block -Kanksa,Dist-Paschim Bardhaman under Durgapur W/s Division,PHE Dte (Part-G) | SM/18745 |  | New | SVS | 1162/DWSD | MONDAL PRECISION PVT LTD | 01-08-2022 | 30-10-2022
73 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Bagdiha & adj. mouzas | SM/03529 | SM/13416 | Augmentation | MVS | 1616/RCD I | SIMA ENTERPRISE | 25-04-2023 | 22-10-2023
74 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1195/DWSD | SHWET BARANI | 11-08-2021 | 10-10-2021
75 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1272/DWSD | JOY GURU ENTERPRISE | 02-09-2021 | 01-11-2021
76 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1272/DWSD | JOY GURU ENTERPRISE | 02-09-2021 | 01-11-2021
77 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1272/DWSD | JOY GURU ENTERPRISE | 02-09-2021 | 01-11-2021
78 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1254/DWSD | PRAVAT SARKAR | 27-08-2021 | 26-10-2021
79 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1253/DWSD | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 27-08-2021 | 26-10-2021
80 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1094/DWSD | JOY GURU ENTERPRISE | 30-07-2021 | 09-08-2021
81 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1094/DWSD | JOY GURU ENTERPRISE | 30-07-2021 | 09-08-2021
82 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 |  |  | MVS | 1310/DWSD | BISHAL ENTERPRISE | 09-12-2020 | 23-01-2021
83 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 142/DWSD | SUBHADEEP DAS | 28-01-2021 | 27-02-2021
84 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 |  |  | MVS | 1283/DWSD | M/S GITASHREE FABRICATION | 03-12-2020 | 17-01-2021
85 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 171/DWSD | PRAVAT SARKAR | 03-02-2021 | 28-02-2021
86 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 |  |  | MVS | 1356/DWSD | AMARANJALI CONSTRUCTION | 09-12-2020 | 23-01-2021
87 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 |  |  | MVS | 1308/DWSD | AMARANJALI CONSTRUCTION | 09-12-2020 | 23-01-2021
88 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/05373 |  | MVS | 1330/DWSD | KIRON ENTERPRISE | 09-12-2020 | 23-01-2021
89 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1746/DWSD | BADAL GHOSH | 15-12-2021 | 25-12-2021
90 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1643/DWSD | PRAVAT SARKAR | 23-11-2021 | 03-12-2021
91 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1662/DWSD | BADAL GHOSH | 25-11-2021 | 05-12-2021
92 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 |  |  | MVS | 1330/DWSD | KIRON ENTERPRISE | 09-12-2020 | 23-01-2021
93 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 1735/DWSD | PRAVAT SARKAR | 13-12-2021 | 23-12-2021
94 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Gourbazar and Ichhapur & adj. mouzas | SM/03522 | SM/07391 | Retrofitting | MVS | 10/DWSD | PRAVAT SARKAR | 04-01-2022 | 19-01-2022
95 | PASCHIM BARDHAMAN | Ground Water Based Piped Water Supply Scheme for Madantor & adj. mouzas | SM/03510 | SM/10845 | Augmentation | MVS | 2450/RCD-I | JOY HIND TUBEWELLS | 13-10-2022 | 11-04-2023
96 | PASCHIM BARDHAMAN | Itapara Water Supply Scheme | SM/01864 | SM/10844 | Augmentation | MVS | 447/RCD-I | KHEPI MAA TRADERS | 12-03-2025 | 11-05-2025
97 | PASCHIM BARDHAMAN | Itapara Water Supply Scheme | SM/01864 | SM/10844 | Augmentation | MVS | 1612/RCD-I | PINKI ENTERPRISE | 06-07-2022 | 04-10-2022
98 | PASCHIM BARDHAMAN | Itapara Water Supply Scheme | SM/01864 | SM/10844 | Augmentation | MVS | 935/RCD-I | KHEPI MAA TRADERS | 26-04-2022 | 25-07-2022
99 | PASCHIM BARDHAMAN | JAMURIA (RURAL PART) WATER SUPPLY SCHEME | SM/01052 | SM/15654 | Augmentation | MVS | 2449/RCD-I | JOY HIND TUBEWELLS | 13-10-2022 | 11-04-2023
100 | PASCHIM BARDHAMAN | JAMURIA (RURAL PART) WATER SUPPLY SCHEME | SM/01052 | SM/15654 | Augmentation | MVS | 1613/RCD I | M/S B.K. CONSTRUCTION | 25-04-2023 | 25-05-2023
101 | PASCHIM BARDHAMAN | Jamuria Municipal & Rural en route Mouzas | SM/02193 | SM/10640 | Augmentation | MVS | 2449/RCD-I | JOY HIND TUBEWELLS | 13-10-2022 | 11-04-2023
102 | PASCHIM BARDHAMAN | Jamuria Municipal & Rural en route Mouzas | SM/02193 | SM/10640 | Augmentation | MVS | 1613/RCD I | M/S B.K. CONSTRUCTION | 25-04-2023 | 25-05-2023
103 | PASCHIM BARDHAMAN | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | SM/18825 | Augmentation | MVS | 1579/DWSD | SUPER SKILL | 21-09-2023 | 20-11-2023
104 | PASCHIM BARDHAMAN | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | SM/18825 | Augmentation | MVS | 1579/DWSD | SUPER SKILL | 21-09-2023 | 20-11-2023
105 | PASCHIM BARDHAMAN | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | SM/18825 | Augmentation | MVS | 1656/DWSD | SUPER SKILL | 05-12-2022 | 17-12-2022
106 | PASCHIM BARDHAMAN | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | SM/18825 | Augmentation | MVS | 1656/DWSD | SUPER SKILL | 05-12-2022 | 17-12-2022
107 | PASCHIM BARDHAMAN | Jemua Piped Water Supply Scheme | SM/06274 | SM/13685 | Retrofitting | MVS | 1071/DWSD | KIRON ENTERPRISE | 12-07-2023 | 06-08-2023
108 | PASCHIM BARDHAMAN | Jemua Piped Water Supply Scheme | SM/06274 | SM/13685 | Retrofitting | MVS | 1394/DWSD | GHOSH & ROY ENTERPRISE | 16-08-2023 | 26-08-2023
109 | PASCHIM BARDHAMAN | Jemua Piped Water Supply Scheme | SM/06274 | SM/13685 | Retrofitting | MVS | 1064/DWSD | M/S MONDAL ENTERPRISE | 12-07-2023 | 06-08-2023
110 | PASCHIM BARDHAMAN | Jemua Piped Water Supply Scheme | SM/06274 | SM/13685 | Retrofitting | MVS | 1085/DWSD | KIRON ENTERPRISE | 16-10-2020 | 16-10-2021
111 | PASCHIM BARDHAMAN | Jemua Piped Water Supply Scheme | SM/06274 | SM/18890 | Augmentation | MVS | 1071/DWSD | KIRON ENTERPRISE | 12-07-2023 | 06-08-2023
112 | PASCHIM BARDHAMAN | Kanchanpur Piped Water Supply Scheme | SM/05351 |  |  | MVS | 930/DWSD | MACHINO TECHNO | 22-09-2020 | 06-11-2020
113 | PASCHIM BARDHAMAN | Kanchanpur Piped Water Supply Scheme | SM/05351 |  |  | MVS | 1443/DWSD | MACHINO TECHNO | 28-12-2020 | 27-01-2021
114 | PASCHIM BARDHAMAN | Kanchanpur Piped Water Supply Scheme | SM/05351 |  |  | MVS | 1318/DWSD | MRITYUNJOY MUKHERJEE AND CO | 09-12-2020 | 23-01-2021
115 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1438/DWSD | MANAS KUMAR SAHA | 28-12-2020 | 11-02-2021
116 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1438/DWSD | MANAS KUMAR SAHA | 28-12-2020 | 11-02-2021
117 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1439/DWSD | DAS & CHAKRABORTY | 28-12-2020 | 22-01-2021
118 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1324/DWSD | M/S KALYANI ENTERPRISE | 09-12-2020 | 23-01-2021
119 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 56/DWSD | RANJIB GHATAK | 13-01-2021 | 07-02-2021
120 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1448/DWSD | GITA CONSTRUCTION | 28-12-2020 | 26-02-2021
121 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1448/DWSD | GITA CONSTRUCTION | 28-12-2020 | 26-02-2021
122 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1448/DWSD | GITA CONSTRUCTION | 28-12-2020 | 26-02-2021
123 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1363/DWSD | MD AAMIR KHAN | 10-12-2020 | 24-01-2021
124 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1363/DWSD | MD AAMIR KHAN | 10-12-2020 | 24-01-2021
125 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1322/DWSD | DAS & CHAKRABORTY | 09-12-2020 | 23-01-2021
126 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1313/DWSD | M/S. D. PALIT & CO. | 09-12-2020 | 23-01-2021
127 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1314/DWSD | UMWELT ENGINEER PVT LTD | 09-12-2020 | 23-01-2021
128 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1445/DWSD | GITA CONSTRUCTION | 28-12-2020 | 22-01-2021
129 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1445/DWSD | GITA CONSTRUCTION | 28-12-2020 | 22-01-2021
130 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 932/DWSD | MD AAMIR KHAN | 25-09-2020 | 09-11-2020
131 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1433/DWSD | SUJAY KUMAR RAY | 28-12-2020 | 26-02-2021
132 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1437/DWSD | M/S. D. PALIT & CO. | 28-12-2020 | 26-02-2021
133 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1375/DWSD | RANJIB GHATAK | 17-09-2021 | 01-11-2021
134 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10210 | Augmentation | MVS | 747/DWSD | MAK CONSTRUCTION CO. | 10-05-2022 | 20-05-2022
135 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10210 | Augmentation | MVS | 816/DWSD | SAIKAT RAY | 21-05-2022 | 20-06-2022
136 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/07391 | Retrofitting | MVS | 1766/DWSD | B. T. M. CONCERN | 16-12-2021 | 15-01-2022
137 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/07391 | Retrofitting | MVS | 1706/DWSD | MD AAMIR KHAN | 08-12-2021 | 07-01-2022
138 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/07391 | Retrofitting | MVS | 1707/DWSD | MD AAMIR KHAN | 08-12-2021 | 07-01-2022
139 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10211 | Augmentation | MVS | 225/DWSD | SAIKAT RAY | 06-02-2023 | 07-05-2023
140 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10210 | Augmentation | MVS | 318/DWSD | AMARANJALI CONSTRUCTION | 20-02-2023 | 12-03-2023
141 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1574/DWSD | MD AAMIR KHAN | 02-11-2022 | 17-11-2022
142 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1575/DWSD | TARA PRASAD SARKAR | 02-11-2022 | 17-11-2022
143 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1576/DWSD | RANJIB GHATAK | 02-11-2022 | 17-11-2022
144 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10211 | Augmentation | MVS | 1361/DWSD | SAIKAT RAY | 20-09-2022 | 24-09-2022
145 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10210 | Augmentation | MVS | 1449/DWSD | MD AAMIR KHAN | 17-10-2022 | 21-10-2022
146 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10209 | Augmentation | MVS | 1161/DWSD | BRINDABAN KONAR | 01-08-2022 | 05-08-2022
147 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1432/DWSD | M/S PIONEER CONSTRUCTION | 28-12-2020 | 26-02-2021
148 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1067/DWSD | TARA PRASAD SARKAR | 12-07-2023 | 11-08-2023
149 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10208 | Augmentation | MVS | 1077/DWSD | MAK CONSTRUCTION CO. | 12-07-2023 | 16-08-2023
150 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/10209 | Augmentation | MVS | 1139/DWSD | JOY GURU ENTERPRISE | 20-07-2023 | 03-09-2023
151 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 |  |  | MVS | 1435/DWSD | ASHOK KUMAR GHOSH | 28-12-2020 | 26-02-2021
152 | PASCHIM BARDHAMAN | KANKSA (PHASE-II) WATER SUPPLY SCHEME | SM/01026 | SM/07391 | Retrofitting | MVS | 1435/DWSD | ASHOK KUMAR GHOSH | 28-12-2020 | 26-02-2021
153 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/10208 | Augmentation | MVS | 445/RCD-I | MAK CONSTRUCTION CO | 12-03-2025 | 11-05-2025
154 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 |  |  | MVS | 1575/DWSD | TARA PRASAD SARKAR | 02-11-2022 | 17-11-2022
155 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/10208 | Augmentation | MVS | 1574/DWSD | MD AAMIR KHAN | 02-11-2022 | 17-11-2022
156 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 |  |  | MVS | 1375/DWSD | RANJIB GHATAK | 17-09-2021 | 01-11-2021
157 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/07391 | Retrofitting | MVS | 1433/DWSD | SUJAY KUMAR RAY | 28-12-2020 | 26-02-2021
158 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/07391 | Retrofitting | MVS | 144/DWSD | M/S KALYANI ENTERPRISE | 28-01-2021 | 14-03-2021
159 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/07391 | Retrofitting | MVS | 1324/DWSD | M/S KALYANI ENTERPRISE | 09-12-2020 | 23-01-2021
160 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 |  |  | MVS | 1324/DWSD | M/S KALYANI ENTERPRISE | 09-12-2020 | 23-01-2021
161 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 |  |  | MVS | 1363/DWSD | MD AAMIR KHAN | 10-12-2020 | 24-01-2021
162 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/10208 | Augmentation | MVS | 1077/DWSD | MAK CONSTRUCTION CO. | 12-07-2023 | 16-08-2023
163 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 |  |  | MVS | 1438/DWSD | MANAS KUMAR SAHA | 28-12-2020 | 11-02-2021
164 | PASCHIM BARDHAMAN | KANKSA & ADJ. MOUZAS WATER SUPPLY SCHEME | SM/00747 | SM/07391 | Retrofitting | MVS | 1067/DWSD | TARA PRASAD SARKAR | 12-07-2023 | 11-08-2023
165 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1195/RCD-I | UNITED CONSTRUCTION | 24-12-2020 | 23-01-2021
166 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1192/RCD-I | M/S MONI TRADERS | 24-12-2020 | 23-01-2021
167 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1191/RCD-I | DAWN CONSTRUCTION | 24-12-2020 | 23-01-2021
168 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1190/RCD-I | SIMA ENTERPRISE | 24-12-2020 | 23-01-2021
169 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1194/RCD-I | DURGADAS MONDAL | 24-12-2020 | 23-01-2021
170 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1159/RCD I | VISUVIOUS | 23-12-2020 | 12-01-2021
171 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1159/RCDI | M/S SOUMYADWIP ENTERPRISE | 24-03-2023 | 23-04-2023
172 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 2026/RCD-I | RANJIB GHATAK | 24-11-2021 | 24-12-2021
173 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 2027/RCD-I | SWATI CORPORATION | 24-11-2021 | 24-12-2021
174 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1080/RCD-I | MACHINO TECHNO | 09-07-2021 | 08-08-2021
175 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1155/RCD I | ZEROTH CONTROL SYSTEM | 23-12-2020 | 12-01-2021
176 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 978/RCD-I | A.K. SIKDAR | 17-06-2021 | 02-07-2021
177 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1158/RCD I | M/S MONDAL CONSTRUCTION | 23-12-2020 | 12-01-2021
178 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1157/RCD I | DHRUBA ENTERPRISE | 23-12-2020 | 12-01-2021
179 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1189/RCD-I | GITASHREE FABRICATION | 24-12-2020 | 23-01-2021
180 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1156 /RCD I | A.K.CONSTRUCTION | 23-12-2020 | 12-01-2021
181 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1193/RCD-I | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 24-12-2020 | 23-01-2021
182 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 1160/RCD I | MS KALYAN ENTERPRISE | 23-12-2020 | 12-01-2021
183 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 2849/RCD I | GOPAL CONSTRUCTION | 02-11-2022 | 17-11-2022
184 | PASCHIM BARDHAMAN | Kendra Kotthamdihi Piped Water Supply Scheme | SM/04898 | SM/07392 | Retrofitting | MVS | 2643/RCDI | JAYANTA DATTA | 28-10-2022 | 12-12-2022
185 | PASCHIM BARDHAMAN | KOTALPUKUR PIPED WATER SUPPLY SCHEME | SM/10996 | SM/07391 | Retrofitting | MVS | 773/DWSD | JOY GURU ENTERPRISE | 17-05-2022 | 01-07-2022
186 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1699/DWSD | JOY GURU ENTERPRISE | 09-12-2022 | 23-01-2023
187 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 387/DWSD | JOY GURU ENTERPRISE | 01-03-2023 | 15-04-2023
188 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 428/DWSD | AMARANJALI CONSTRUCTION | 13-03-2023 | 27-04-2023
189 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 270/DWSD | D. S. ENTERPRISE | 16-02-2023 | 02-04-2023
190 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 1778/DWSD | ALOK ENTERPRISE | 23-12-2022 | 25-06-2023
191 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 1779/DWSD | UMWELT ENGINEER PVT LTD | 23-12-2022 | 04-01-2023
192 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 05/DWSD | IJABUL SEKH | 02-01-2023 | 06-01-2023
193 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 05/DWSD | IJABUL SEKH | 02-01-2023 | 06-01-2023
194 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 45/DWSD | RANJIB GHATAK | 11-01-2023 | 25-02-2023
195 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 272/DWSD | GHOSH ENTERPRISE | 16-02-2023 | 02-04-2023
196 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 29/DWSD | PRAVAT SARKAR | 09-01-2023 | 23-02-2023
197 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 28/DWSD | M/S MONDAL ENTERPRISE | 09-01-2023 | 23-02-2023
198 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 27/DWSD | M/S BADAL GHOSH | 09-01-2023 | 23-02-2023
199 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1711/DWSD | SAIKAT RAY | 09-12-2022 | 23-01-2023
200 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 26/DWSD | KIRON ENTERPRISE | 09-01-2023 | 23-02-2023
201 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 427/DWSD | TARA PRASAD SARKAR | 13-03-2023 | 27-04-2023
202 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1690/DWSD | RANJIB GHATAK | 09-12-2022 | 23-01-2023
203 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 426/DWSD | DIP CONSTRUCTION | 13-03-2023 | 27-04-2023
204 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 634/DWSD | DIP CONSTRUCTION | 21-04-2022 | 11-05-2022
205 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 45/DWSD | M.R. CONSTRUCTION CO. | 25-01-2017
206 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1698/DWSD | ASHA CONSTRUCTION | 09-12-2022 | 23-01-2023
207 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 1762/RCD I | MD AAMIR KHAN | 16-05-2023 | 12-11-2023
208 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1277/DWSD | PRADIP CHOUDHARY | 07-08-2023 | 21-09-2023
209 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 739/DWSD | KIRON ENTERPRISE | 22-05-2023 | 21-07-2023
210 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 1762/RCD I | MD AAMIR KHAN | 16-05-2023 | 12-11-2023
211 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/11454 | Augmentation | MVS | 1066/DWSD | BASANTI TRADERS | 12-07-2023 | 11-08-2023
212 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 271/DWSD | SHWET BARANI | 18-07-2017
213 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 360/DWSD | GHOSH ENTERPRISE | 08-04-2019
214 | PASCHIM BARDHAMAN | Modified Raniganj Cold Field Area Part -III Water Supply Scheme | SM/01938 | SM/12726 | Augmentation | MVS | 148/RCD-I | M/S MONDAL ENTERPRISE | 08-01-2025 | 22-02-2025
215 | PASCHIM BARDHAMAN | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 |  | New | MVS | 1174/DWSD | SK. ALIM | 02-08-2022 | 14-08-2022
216 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 109/AMD | UNIQUE ENTERPRISE | 22-01-2021 | 21-02-2021
217 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 110/AMD | M/S SWAPAN BANERJEE | 22-01-2021 | 21-02-2021
218 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 101/AMD | M/S UNIVERSAL CARRIERS | 22-01-2021 | 21-02-2021
219 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 102/AMD | M/S JIT ENTERPRISE | 22-01-2021 | 21-02-2021
220 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 108/AMD | UNIQUE ENTERPRISE | 22-01-2021 | 21-02-2021
221 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 107/AMD | ANANYA CONSTRUCTION | 22-01-2021 | 21-02-2021
222 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 106/AMD | HINDUSTHAN CONSULTANT FIRM | 22-01-2021 | 21-02-2021
223 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 105/AMD | ANANYA CONSTRUCTION | 22-01-2021 | 21-02-2021
224 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 104/AMD | PESTCO INDIA | 22-01-2021 | 21-02-2021
225 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 103/AMD | PESTCO INDIA | 22-01-2021 | 21-02-2021
226 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 112/AMD | VIKING TRADERS | 22-01-2021 | 21-02-2021
227 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 113/AMD | ANANYA CONSTRUCTION | 22-01-2021 | 21-02-2021
228 | PASCHIM BARDHAMAN | Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme | SM/03198 |  |  | MVS | 111/AMD | M/S JIT ENTERPRISE | 22-01-2021 | 21-02-2021
229 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/10641 | Augmentation | MVS | 2853/RCD I | MD SARFARAZ ALAM | 02-11-2022 | 17-11-2022
230 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 2853/RCD I | MD SARFARAZ ALAM | 02-11-2022 | 17-11-2022
231 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/10641 | Augmentation | MVS | 2452/RCD-I | M/S PIONEER CONSTRUCTION | 13-10-2022 | 11-04-2023
232 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 3212/RCD-I | DAS & SARKAR ENTERPRISE | 26-12-2024 | 20-01-2025
233 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 1609/RCD-I | UMA ENTERPRISE | 06-07-2022 | 04-10-2022
234 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 1741/RCD-I | UNITED CONSTRUCTION | 18-07-2024 | 01-09-2024
235 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 2482/RCD I | SIMA ENTERPRISE | 17-10-2022 | 01-12-2022
236 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 2211/RCD-I | UNITED CONSTRUCTION | 14-09-2022 | 29-10-2022
237 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11576 | Augmentation | MVS | 2836/RCDI | M/S KALYANI ENTERPRISE | 28-10-2022 | 27-11-2022
238 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 2483/RCD I | SOMNATH SAMANTA | 17-10-2022 | 01-12-2022
239 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/10641 | Augmentation | MVS | 1608/RCD-I | AMAR CONSTRUCTION | 06-07-2022 | 04-10-2022
240 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11576 | Augmentation | MVS | 2853/RCD I | MD SARFARAZ ALAM | 02-11-2022 | 17-11-2022
241 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/10641 | Augmentation | MVS | 1002/RCDI | SINGHA ROY & CO. | 22-03-2023 | 20-07-2023
242 | PASCHIM BARDHAMAN | ONDAL (RURAL PART) WATER SUPPLY SCHEME | SM/01053 | SM/11575 | Augmentation | MVS | 3218/RCD-I | DAS & SARKAR ENTERPRISE | 26-12-2024 | 20-01-2025
243 | PASCHIM BARDHAMAN | Piped water supply scheme for Amritnagar Zone within RCFA Part-II Area under RCFA Division - I, PHE Dte. | SM/03960 | SM/11986 | Augmentation | MVS | 2455/RCD-I | MACHINO TECHNO | 13-10-2022 | 11-04-2023
244 | PASCHIM BARDHAMAN | Piped water supply scheme for Amritnagar Zone within RCFA Part-II Area under RCFA Division - I, PHE Dte. | SM/03960 | SM/16777 | Augmentation | MVS | 2455/RCD-I | MACHINO TECHNO | 13-10-2022 | 11-04-2023
245 | PASCHIM BARDHAMAN | Piped water supply scheme for Amritnagar Zone within RCFA Part-II Area under RCFA Division - I, PHE Dte. | SM/03960 | SM/13418 | Augmentation | MVS | 37/RCD I | TARAPRASAD SARKAR | 11-01-2023 | 25-02-2023
246 | PASCHIM BARDHAMAN | Piped water supply scheme for Amritnagar Zone within RCFA Part-II Area under RCFA Division - I, PHE Dte. | SM/03960 | SM/13418 | Augmentation | MVS | 36/RCD I | M/S SINGH & KONAR CONSTRUCTION | 11-01-2023 | 25-02-2023
247 | PASCHIM BARDHAMAN | Piped water supply scheme for Amritnagar Zone within RCFA Part-II Area under RCFA Division - I, PHE Dte. | SM/03960 | SM/13418 | Augmentation | MVS | 35/RCD I | DAS & CHAKRABORTY | 11-01-2023 | 11-04-2023
248 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1156/DWSD | M/S BADAL GHOSH | 28-10-2020 | 12-12-2020
249 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1304/DWSD | M/S MONDAL ENTERPRISE | 09-12-2020 | 23-01-2021
250 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1449/DWSD | M/S BADAL GHOSH | 28-12-2020 | 22-01-2021
251 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1156/DWSD | M/S BADAL GHOSH | 28-10-2020 | 12-12-2020
252 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/05372 |  | MVS | 1169/DWSD | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 29-11-2019
253 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1253/DWSD | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 27-08-2021 | 26-10-2021
254 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 1272/DWSD | JOY GURU ENTERPRISE | 02-09-2021 | 01-11-2021
255 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 1094/DWSD | JOY GURU ENTERPRISE | 30-07-2021 | 09-08-2021
256 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1273/DWSD | RANJIB GHATAK | 02-09-2021 | 17-09-2021
257 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1290/DWSD | RANJIB GHATAK | 07-09-2021 | 22-09-2021
258 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 25/DWSD | RANJIB GHATAK | 06-01-2022 | 21-01-2022
259 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1283/DWSD | RANJIB GHATAK | 06-09-2021 | 21-09-2021
260 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 1634/DWSD | BABA LOKENATH ENTERPRISE | 22-11-2021 | 22-12-2021
261 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 244/DWSD | M/S BADAL GHOSH | 22-02-2022 | 19-03-2022
262 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1097/DWSD | M/S MONDAL ENTERPRISE | 16-10-2020 | 16-10-2021
263 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 660/DWSD | M/S MONDAL ENTERPRISE | 16-07-2020
264 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 340/DWSD. | BABA LOKNATH ENTERPRISE | 31-03-2020
265 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07524 | Retrofitting | MVS | 1012/DWSD | BABA LOKNATH ENTERPRISE | 08-10-2020 | 23-10-2020
266 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 1662/DWSD | BADAL GHOSH | 25-11-2021 | 05-12-2021
267 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Jamgara-Jagannathpur and its adjoining mouzas | SM/03785 | SM/07391 | Retrofitting | MVS | 1746/DWSD | BADAL GHOSH | 15-12-2021 | 25-12-2021
268 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Krishnapur & Adjoining Mouzas | SM/04557 | SM/07391 | Retrofitting | MVS | 346/DWSD | THE STAR & CO | 17-03-2022 | 01-04-2022
269 | PASCHIM BARDHAMAN | Piped Water Supply Scheme for Krishnapur & Adjoining Mouzas | SM/04557 | SM/07520 |  | MVS | 1447/DWSD | THE STAR & CO | 28-12-2020 | 17-01-2021
270 | PASCHIM BARDHAMAN | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 |  | New | MVS | 504/A/DWSD | BISHAL ENTERPRISE | 28-03-2023 | 07-05-2023
271 | PASCHIM BARDHAMAN | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 |  | New | MVS | 580/DWSD | SAIKAT RAY | 10-04-2023 | 20-05-2023
272 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12222 | Augmentation | MVS | 2868/RCD-I | MACHINO TECHNO | 06-10-2023 | 05-11-2023
273 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1876/RCD-I | B.T.M CONCERN | 28-10-2021 | 27-11-2021
274 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12032 | Augmentation | MVS | 1762/RCD I | MD AAMIR KHAN | 16-05-2023 | 12-11-2023
275 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 1742/RCD I | D.S.C. CONCERN | 11-05-2023 | 26-05-2023
276 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12220 | Augmentation | MVS | 998/RCDI | SWATI CORPORATION | 22-03-2023 | 20-06-2023
277 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2129/RCD-I | M/S SUBHRADEEP | 29-11-2021 | 29-12-2021
278 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12042 | Augmentation | MVS | 1606/RCD I | JOY HIND TUBEWELLS | 25-04-2023 | 24-07-2023
279 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12030 | Augmentation | MVS | 1764/RCD I | MRITYUNJOY MUKHERJEE & CO. | 16-05-2023 | 13-09-2023
280 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 198/RCD-I | B M SARKAR | 28-01-2022 | 27-02-2022
281 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2491/RCD-I | TARA CONSTRUCTION | 31-12-2021 | 30-01-2022
282 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2323/RCD-I | GITASHREE FABRICATION | 16-12-2021 | 15-01-2022
283 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2324/RCD-I | A. CONSTRUCTION CO. | 16-12-2021 | 15-01-2022
284 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2325/RCD-I | JYOGOMAYA ENTERPRISE | 16-12-2021 | 15-01-2022
285 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2326/RCD-I | M/S B.K. CONSTRUCTION | 16-12-2021 | 15-01-2022
286 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2327/RCD-I | ASHA CONSTRUCTION | 16-12-2021 | 15-01-2022
287 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2328/RCD-I | MD AAMIR KHAN | 16-12-2021 | 15-01-2022
288 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2329/RCD-I | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 16-12-2021 | 15-01-2022
289 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 1880/RCD-I | R B ENTERPRISE | 28-10-2021 | 27-11-2021
290 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2124/RCD-I | A.K.CONSTRUCTION | 29-11-2021 | 29-12-2021
291 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2125/RCD-I | UNITED CONSTRUCTION | 29-11-2021 | 29-12-2021
292 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2126/RCD-I | DURGADAS MONDAL | 29-11-2021 | 29-12-2021
293 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2127/RCD-I | SIMA ENTERPRISE | 29-11-2021 | 29-12-2021
294 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2128/RCD-I | M/S KALYANI ENTERPRISE | 29-11-2021 | 29-12-2021
295 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 2130/RCD-I | D.S. ENTERPRISE | 29-11-2021 | 29-12-2021
296 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 2131/RCD-I | M/S B.K. CONSTRUCTION | 29-11-2021 | 29-12-2021
297 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 2132/RCD-I | KHEPI MAA TRADERS | 29-11-2021 | 29-12-2021
298 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 2133/RCD-I | MRITYUNJOY MUKHERJEE & CO. | 29-11-2021 | 29-12-2021
299 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2333/RCD-I | TARAPRASAD SARKAR | 17-12-2021 | 16-01-2022
300 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 120/RCD-I | GLOBAL CONSTRUCTION | 20-01-2022 | 19-02-2022
301 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 2332/RCD-I | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 17-12-2021 | 16-01-2022
302 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1874/RCD-I | MD. JAWED KHAN | 28-10-2021 | 27-11-2021
303 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1877/RCD-I | SIMA ENTERPRISE | 28-10-2021 | 27-11-2021
304 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 2145/RCD-I | DAS & CHAKRABORTY | 29-11-2021 | 29-03-2022
305 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1878/RCD-I | M/S K & KONAR CONSTRUCTION | 28-10-2021 | 27-11-2021
306 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1879/RCD-I | SOMNATH SAMANTA | 28-10-2021 | 27-11-2021
307 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1875/RCD-I | UNITED CONSTRUCTION | 28-10-2021 | 27-11-2021
308 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09060 | Retrofitting | MVS | 1881/RCD-I | A. CONSTRUCTION CO. | 28-10-2021 | 27-11-2021
309 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09388 | Retrofitting | SVS | 2143/RCD-I | GITA CONSTRUCTION | 29-11-2021 | 29-03-2022
310 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09388 | Retrofitting | SVS | 2144/RCD-I | MD AAMIR KHAN | 29-11-2021 | 29-03-2022
311 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1870/RCD-I | JAYANTA DATTA | 28-10-2021 | 27-11-2021
312 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1867/RCD-I | DAS & CHAKRABORTY | 28-10-2021 | 27-11-2021
313 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1869/RCD-I | UMA ENTERPRISE | 28-10-2021 | 27-11-2021
314 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1871/RCD-I | RUBY CONSTRUCTION | 28-10-2021 | 27-11-2021
315 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1872/RCD-I | MS KALYAN ENTERPRISE | 28-10-2021 | 27-11-2021
316 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1873/RCD-I | SNEHA ELECTRIC | 28-10-2021 | 27-11-2021
317 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12025 | Augmentation | MVS | 954/RCDI | M/S PIONEER CONSTRUCTION | 20-03-2023 | 18-07-2023
318 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 1159/RCDI | M/S SOUMYADWIP ENTERPRISE | 24-03-2023 | 23-04-2023
319 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09387 | Retrofitting | SVS | 1155/ RCD I | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 24-03-2023 | 23-04-2023
320 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 1116/RCD-I | BABA LOKNATH ENTERPRISE | 23-03-2023 | 21-06-2023
321 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12029 | Augmentation | MVS | 1115/ RCD I | M/S B.K. CONSTRUCTION | 23-03-2023 | 21-06-2023
322 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 1156/ RCD I | GOPAL CONSTRUCTION | 24-03-2023 | 23-04-2023
323 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12216 | Augmentation | MVS | 1158/RCD-I | ANAMIKA CONSTRUCTION | 24-03-2023 | 23-04-2023
324 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12210 | Augmentation | MVS | 1390/RCD I | M/S SRI MAHADEO ENTERPRISES | 11-04-2023 | 10-07-2023
325 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 1112/ RCD I | UNITED CONSTRUCTION | 23-03-2023 | 21-06-2023
326 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12029 | Augmentation | MVS | 1112/ RCD I | UNITED CONSTRUCTION | 23-03-2023 | 21-06-2023
327 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 1118/RCD-I | UNITED CONSTRUCTION | 23-03-2023 | 21-06-2023
328 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 1604/RCD I | PINKI ENTERPRISE | 25-04-2023 | 22-10-2023
329 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12222 | Augmentation | MVS | 1607/RCD I | MD AAMIR KHAN | 25-04-2023 | 24-07-2023
330 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 1707/ RCD I | MD. JAWED KHAN | 03-05-2023 | 01-08-2023
331 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12215 | Augmentation | MVS | 1002/RCDI | SINGHA ROY & CO. | 22-03-2023 | 20-07-2023
332 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12227 | Augmentation | MVS | 818/RCDI | ASHA CONSTRUCTION | 10-03-2023 | 24-04-2023
333 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/05433 |  | MVS | 2847/RCD I | DHRUBA ENTERPRISE | 02-11-2022 | 17-11-2022
334 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12033 | Augmentation | MVS | 2847/RCD I | DHRUBA ENTERPRISE | 02-11-2022 | 17-11-2022
335 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 2847/RCD I | DHRUBA ENTERPRISE | 02-11-2022 | 17-11-2022
336 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 |  |  | MVS | 2455/RCD-I | MACHINO TECHNO | 13-10-2022 | 11-04-2023
337 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12042 | Augmentation | MVS | 3160/RCD-I | KRISHNA KUMAR TODI HUF | 13-12-2022 | 12-01-2023
338 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 279/RCD-I | M/S U.G. ENTERPRISE | 01-02-2022 | 03-03-2022
339 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09389 | Retrofitting | SVS | 2212/RCD-I | UNITED CONSTRUCTION | 14-09-2022 | 14-10-2022
340 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/07392 | Retrofitting | MVS | 278/RCD-I | M/S MONDAL CONSTRUCTION | 01-02-2022 | 03-03-2022
341 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12210 | Augmentation | MVS | 622/RCD-I | M/S KALYAN ENTERPRISE | 27-02-2024 | 13-03-2024
342 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12219 | Augmentation | MVS | 2132/RCD-I | UNITED CONSTRUCTION | 27-08-2024 | 26-09-2024
343 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12223 | Augmentation | MVS | 2132/RCD-I | UNITED CONSTRUCTION | 27-08-2024 | 26-09-2024
344 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12026 | Augmentation | MVS | 1008/RCD-I | M/S MONDAL ENTERPRISE | 16-03-2024 | 31-03-2024
345 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/12026 | Augmentation | MVS | 159/RCD-I | JAI MAHARAJ ENTERPRISE | 08-01-2025 | 22-02-2025
346 | PASCHIM BARDHAMAN | R.C.F.A PART- II WATER SUPPLY SCHEME | SM/03130 | SM/09059 | Retrofitting | MVS | 1868/RCD-I | DAWN CONSTRUCTION | 28-10-2021 | 27-11-2021
347 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 159/RCD-I | JAI MAHARAJ ENTERPRISE | 08-01-2025 | 22-02-2025
348 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | Camp-02-Srirampur/AE-II/2024-2025 | JAI MAHARAJ ENTERPRISE | 31-07-2024 | 27-01-2025
349 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1610/RCD-I | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 06-07-2022 | 04-10-2022
350 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1379/RCD-I | MRITYUNJOY MUKHERJEE & CO. | 17-06-2022 | 14-12-2022
351 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 2868/RCD-I | MACHINO TECHNO | 06-10-2023 | 05-11-2023
352 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1039/RCD-I | DAS & CHAKRABORTY | 10-05-2022 | 06-11-2022
353 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1613/RCD-I | KONAR CONSTRUCTION | 06-07-2022 | 04-10-2022
354 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1761/RCD I | MD AAMIR KHAN | 16-05-2023 | 12-11-2023
355 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1020/RCD-I | SWATI CORPORATION | 06-05-2022 | 02-11-2022
356 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1742/RCD-I | TARA CONSTRUCTION | 18-07-2024 | 01-09-2024
357 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 129/RCD-I | SRI KRISHNA ENTERPRISE | 08-01-2025 | 22-02-2025
358 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 2544/RCD-I | SWATI CORPORATION. | 29-10-2024 | 13-12-2024
359 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | Camp-02-Zone-IX/AE/2024-2025 | JAI MAHARAJ ENTERPRISE | 12-07-2024 | 29-12-2024
360 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1214/RCD-I | RANJIB GHATAK | 30-05-2022 | 28-08-2022
361 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1007/RCD-I | GITASREE FABRICATION | 05-05-2022 | 03-08-2022
362 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1038/RCD-I | ASHA CONSTRUCTION | 10-05-2022 | 06-11-2022
363 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 935/RCD-I | KHEPI MAA TRADERS | 26-04-2022 | 25-07-2022
364 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 934/RCD-I | SRI KRISHNA ENTERPRISE | 26-04-2022 | 25-07-2022
365 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 933/RCD-I | M/S K & KONAR CONSTRUCTION | 26-04-2022 | 25-07-2022
366 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 932/RCD-I | DIP CONSTRUCTION | 26-04-2022 | 25-07-2022
367 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1699/RCD-I | UMA ENTERPRISE | 13-07-2022 | 27-08-2022
368 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1704/RCD-I | SNEHA ELECTRIC | 14-07-2022 | 28-08-2022
369 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1700/RCD-I | R B ENTERPRISE | 14-07-2022 | 28-08-2022
370 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1702/RCD-I | UNITED CONSTRUCTION | 14-07-2022 | 28-08-2022
371 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1611/RCD-I | UNITED CONSTRUCTION | 06-07-2022 | 04-10-2022
372 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1612/RCD-I | PINKI ENTERPRISE | 06-07-2022 | 04-10-2022
373 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1701/RCD-I | VISUVIOUS | 14-07-2022 | 28-08-2022
374 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1329/RCD-I | SWATI CORPORATION | 09-06-2022 | 06-12-2022
375 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 2847/RCD I | DHRUBA ENTERPRISE | 02-11-2022 | 17-11-2022
376 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1707/RCD-I | M/S B.K. CONSTRUCTION | 14-07-2022 | 28-08-2022
377 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 1708/RCD-I | DAWN CONSTRUCTION | 15-07-2022 | 29-08-2022
378 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 488/RCD I | SUBHADEEP DAS | 03-02-2023 | 05-03-2023
379 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 2404/RCD-I | GITA CONSTRUCTION | 30-09-2022 | 29-03-2023
380 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/09916 | Augmentation | MVS | 497/RCD-I | UNITED CONSTRUCTION | 24-02-2022 | 25-05-2022
381 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/07562 | Retrofitting | MVS | 950/RCD-I | UMA ENTERPRISE | 07-06-2021 | 07-07-2021
382 | PASCHIM BARDHAMAN | R.C.F.A PART-I WATER SUPPLY SCHEME | SM/03118 | SM/07562 | Retrofitting | MVS | 951/RCD-I | TARAPRASAD SARKAR | 07-06-2021 | 07-07-2021
383 | PASCHIM BARDHAMAN | Roshna and adj. mouzas water supply scheme | SM/02987 | SM/09062 | Retrofitting | MVS | 1863/RCD-I | SRI KRISHNA ENTERPRISE | 28-10-2021 | 27-11-2021
384 | PASCHIM BARDHAMAN | Roshna and adj. mouzas water supply scheme | SM/02987 | SM/10642 | Augmentation | MVS | 1607/RCD-I | SRI KRISHNA ENTERPRISE | 06-07-2022 | 02-01-2023
385 | PASCHIM BARDHAMAN | Roshna and adj. mouzas water supply scheme | SM/02987 | SM/09062 | Retrofitting | MVS | 1862/RCD-I | M/S MONI TRADERS | 28-10-2021 | 27-11-2021
386 | PASCHIM BARDHAMAN | Roshna and adj. mouzas water supply scheme | SM/02987 | SM/09062 | Retrofitting | MVS | 1864/RCD-I | MAK CONSTRUCTION CO. | 28-10-2021 | 27-11-2021
387 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/10203 | Augmentation | MVS | 336/DWSD | BISHAL ENTERPRISE | 31-08-2015
388 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/07391 | Retrofitting | MVS | 144/DWSD | M/S KALYANI ENTERPRISE | 28-01-2021 | 14-03-2021
389 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/07391 | Retrofitting | MVS | 145/DWSD | M/S KALYANI ENTERPRISE | 28-01-2021 | 19-03-2021
390 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/07391 | Retrofitting | MVS | 1783/DWSD | M/S KALYANI ENTERPRISE | 21-12-2021 | 20-01-2022
391 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/10203 | Augmentation | MVS | 327/DWSD | DARPAN DAS & CO. | 20-02-2023 | 27-03-2023
392 | PASCHIM BARDHAMAN | RUPGANJ & ITS ADJ.MOUZAS | SM/00404 | SM/10203 | Augmentation | MVS | 397/DWSD | M/S BADAL GHOSH | 28-03-2022 | 27-04-2022
393 | PASCHIM BARDHAMAN | Semalya Piped Water Supply Scheme | SM/05554 | SM/12024 | Retrofitting | MVS | 2029/RCD-I | SWATI CORPORATION | 30-08-2022 | 26-02-2023
394 | PASCHIM BARDHAMAN | Semalya Piped Water Supply Scheme | SM/05554 | SM/12024 | Retrofitting | MVS | 3230/RCD I | A. CONSTRUCTION CO. | 19-12-2022 | 19-03-2023
395 | PASCHIM BARDHAMAN | Semalya Piped Water Supply Scheme | SM/05554 | SM/12024 | Retrofitting | MVS | 3233/RCD I | DAWN CONSTRUCTION | 19-12-2022 | 19-03-2023
396 | PASCHIM BARDHAMAN | Shyambazar Piped water Supply Scheme | SM/11228 |  | New | MVS | 1648/DWSD | DUTTA ENTERPRISE | 02-12-2022 | 14-12-2022
397 | PASCHIM BARDHAMAN | Shyambazar Piped water Supply Scheme | SM/11228 | SM/18826 | Augmentation | MVS | 1648/DWSD | DUTTA ENTERPRISE | 02-12-2022 | 14-12-2022
398 | PASCHIM BARDHAMAN | Telipara Piped Water Supply Scheme. | SM/10311 | SM/10311 | New | MVS | 648/DWSD | M/S SANTANU PALIT & CO. | 21-04-2022 | 16-05-2022
399 | PASCHIM BARDHAMAN | Telipara Piped Water Supply Scheme. | SM/10311 | SM/10311 | New | MVS | 555/DWSD | M/S PROCHESTA ENTERPRISE | 13-09-2018
400 | PASCHIM BARDHAMAN | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 |  | New | MVS | 762/DWSD | JOY GURU ENTERPRISE | 22-05-2023 | 26-06-2023
401 | PASCHIM BARDHAMAN | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 |  | New | MVS | 811/DWSD | CHATTERJEE CONSTRUCTION | 29-05-2023 | 03-07-2023
402 | PASCHIM BARDHAMAN | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 |  | New | MVS | 810/DWSD | BASANTI TRADERS | 29-05-2023 | 03-07-2023
403 | PASCHIM BARDHAMAN | Tilakchandrapur Piped Water Supply Scheme | SM/05403 |  |  | MVS | 155/DWSD | AMARANJALI CONSTRUCTION | 28-01-2021 | 14-03-2021
404 | PASCHIM BARDHAMAN | Tilakchandrapur Piped Water Supply Scheme | SM/05403 | SM/07391 | Retrofitting | MVS | 1826/DWSD | SHWET BARANI | 05-12-2023 | 06-06-2024
405 | PASCHIM BARDHAMAN | Tilakchandrapur Piped Water Supply Scheme | SM/05403 | SM/18886 | Augmentation | MVS | 1826/DWSD | SHWET BARANI | 05-12-2023 | 06-06-2024
406 | PASCHIM BARDHAMAN | Tilakchandrapur Piped Water Supply Scheme | SM/05403 |  |  | MVS | 1229/DWSD | S K ALIM | 23-08-2021 | 07-10-2021
407 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 1167/RCD-I | MRITYUNJOY MUKHERJEE & CO. | 23-12-2020 | 22-01-2021
408 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 1187/RCD-I | A. CONSTRUCTION CO. | 24-12-2020 | 23-01-2021
409 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 1185/RCD-I | SWATI CORPORATION | 24-12-2020 | 23-01-2021
410 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 1186/RCD-I | M/S B.K. CONSTRUCTION | 24-12-2020 | 23-01-2021
411 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 279/RCD-I | M/S U.G. ENTERPRISE | 01-02-2022 | 03-03-2022
412 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 2468/RCD I | GOPAL CONSTRUCTION | 31-12-2021 | 10-01-2022
413 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 2465/RCD I | D.S.C. CONCERN | 31-12-2021 | 07-01-2022
414 | PASCHIM BARDHAMAN | Water supply scheme for Ratibati and adjoining mouzas using Sub-Surface water of River Damodar | SM/03894 | SM/07392 | Retrofitting | MVS | 1188/RCD-I | SOMNATH SAMANTA | 24-12-2020 | 23-01-2021