## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Kharibari W/S Scheme at Kharibari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 818/SWSD | 13/08/2021 |  | ENVIROTECH SOLUTIONS | 3.08 | 3.08 | 100
2 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Soil Investigation of Kharibari Zone -II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 387/SSD | 20/07/2022 |  | G. TECH INDIA | 0.99 | 0.99 | 100
3 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | BP-2021-22-105 | 25/03/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 49.61 | 0 | 0
4 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  |  | 08/08/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 19.19 | 0 | 0
5 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | 1325/SWSD | 14/09/2022 |  | GANPATI CONSTRUCTION CO | 15.45 | 12.1 | 100
6 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Laying distribution system (Part-C) and allied works with providing functional household tap connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 2429/SWSD | 21/03/2022 |  | HIMADRI DAM & CO. | 77.67 | 37.94 | 62
7 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement as per Model Approved Drawing at Tubewell site for different Water Supply Scheme under Siliguri W/S Division, P. H. Engineering Dte. (Name of Scheme : Kharibari Zone-I & II PWSS (Two Nos.) | Assistant Engineer(Civil) | Junior Engineer(Civil) | 334/SWSD | 08/05/2023 |  | SWAPAN CHANDRA DAS | 11.67 | 11.67 | 100
8 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Material Requisition To Resource Division |  |  | 2175/SWSD | 11/02/2022 |  | Resource Division | 51.57 | 0 | 0
9 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Material Requisition To Resource Division |  |  | 1451/SWSD | 29/09/2022 |  | Resource Division | 26.79 | 0 | 0
10 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | New Service Connection Charge for GURUDAYALJOTE W/S Scheme, T/W No. I, Zone-I under KHARIBARI CCC, [APPLICATION NO. 4003055480, Reference ID : 402933291] |  |  | BP/22-23/122 | 16/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0
11 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | New Service Connection Charge for PWD MORE W/S Scheme, T/W No. I, Zone-II under KHARIBARI CCC, [APPLICATION NO. 4003055466, Reference ID : 402933292] |  |  | BP/22-23/122 | 16/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0
12 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Hiring of vehicle for the office of the Siliguri Sub Division PHE Dte. Assistant Engineer |  |  | BP-2023-24-120 | 19/10/2023 |  | SUDIP BASAK | 0.74 | 0 | 0
13 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Resources payment for Different Water Supply Scheme |  |  | BP-2022-23-141 | 13/03/2023 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 19.19 | 0 | 0
14 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Construction of 300 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Connection (FHTC) and allied works at distribution pipe line of Kharibari Zone -II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 911/SWSD | 25/07/2022 |  | ARUN KUMAR SHRIVASTAVA | 240.16 | 131.48 | 2
15 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising main and distribution system (Paret-A) allied with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme and allied works Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 872/SWSD | 21/07/2022 |  | PALLAB BHOWAL | 232.84 | 133.28 | 20
16 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Laying distribution system (Part-B) and allied works with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 15. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 873/SWSD | 21/07/2022 |  | PALLAB BHOWAL | 91 | 45.42 | 73
17 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | 2931/SWSD | 30/10/2024 |  | ARUN KUMAR SHRIVASTAVA | 27.93 | 0 | 0
18 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIBARI ZONE - I (TW No. I) and ZONE - II (TW No. I) PIPED WATER SUPPLY SCHEME , in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 493/NMD | 28/04/2023 |  | SARKAR ELECTRIC | 22.33 | 22.33 | 80
19 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | Augmentation | Sinking of Tubewell By Reverse Rotary Method at 2nd site(KESORDOBA) in replacsmenil of damaged Tube well,KHARIBARI PWSS (ZONE-II) Block: Khoribari, Dist: Darjeeling Under Siliguri W/S Division P.H.E.Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | 2533/swsd | 18/09/2024 |  | NARENDRA KUMAR | 8.71 | 5.28 | 85
Total | [12 empty] | 900.42 | 403.55 | 44.82