## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | DARJEELING | Kurseong Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | SM/10799 | New | SURFACE WATER BASED KOPCHI GAON PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | 601/NKWSMD | 26/05/2022 |  | HIMALI CONSTRUCTION COMPANY | 26.02 | 9.44 | 100
2 | DARJEELING | Kurseong Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | SM/10799 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.11.2024 to 31.12.2024. | Assistant Engineer II | Junior Engineer I | 2047/NKWSMD | 28/10/2024 |  | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
3 | DARJEELING | Kurseong Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | SM/10799 | New | (Continuation) Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.11.2024 to 31.12.2024. | Assistant Engineer II | Junior Engineer I | 2046/NKWSMD | 28/10/2024 |  | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
Total | [12 empty] | 27.2 | 9.44 | 34.7