## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | Material Requisition To Resource Division |  |  | 2557/NKWSMD | 17/02/2023 |  | Resource Division | 8.43 | 0 | 0
2 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | Material Requisition To Resource Division |  |  | 2714/NKWSMD | 03/03/2023 |  | Resource Division | 8.43 | 0 | 0
3 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. | Assistant Engineer |  | 2519/NKWSMD | 15/02/2023 |  | GARGO TRADERS | 1586.68 | 0 | 70
4 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | External Water Supply Works at 10 Bedded Hospital, Ghoom, Darjeeling, GTA |  |  | 1507/NKWSMD | 06/12/2023 |  | DHIRAJ TAMANG | 17.88 | 0 | 35
5 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | 1591/NKWSMD | 29/12/2023 |  | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
6 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months). | Assistant Engineer II | Junior Engineer I | 1457/NKWSMD | 30/11/2023 |  | THE ELECTRIC SPHERE | 0.79 | 0.79 | 100
7 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 30/11/2023 (2 Months). | Assistant Engineer II | Junior Engineer I | 1139/NKWSMD | 29/09/2023 |  | THE ELECTRIC SPHERE | 0.79 | 0.79 | 100
8 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | Water Supply Scheme For Ghoom Pahar Forest under JAL JEEWAN MISSION within Jorebunglow Sukhia Pokhri Block,District-Darjeeling Detail - (SW No. : SW/140971/2023) |  |  | BP-2024-25-291 | 24/09/2024 |  | DIVISIONAL FOREST OFFICER | 6.45 | 0 | 0
9 | DARJEELING | Darjeeling Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | 2652/NKWSMD | 28/02/2023 |  | KAMAKHAYA CONSTRUCTION | 8.43 | 0 | 80
Total | [12 empty] | 1638.82 | 1.57 | 0.1