## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | LDS BHUJARI PARA KRANTI ZONE II |  |  | BP-2021-22-439 | 26/03/2022 |  | BARUN KUMAR DUTTA | 4.7 | 0 | 0
2 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 123 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Augmentation of Ramsai Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | 633/JD | 07/03/2022 |  | MECHANO TRADING CO. | 15.35 | 13.91 | 0
3 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | 217/JD | 24/01/2022 |  | GOURAB GUHA ROY | 11.36 | 11.36 | 100
4 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 2228/JD | 27/12/2021 |  | SANKAR DAS | 11.33 | 11.33 | 100
5 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Laying Distribution System ( node 2-4-287-288-289-290-291-292 & node 5-134) for Augmentation of Ramsai Piped Water Supply Scheme under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. Block-Maynaguri. District- Jalpaiguri. | Assistant Engineer | Junior Engineer | 730/JD | 22/03/2023 |  | R.S CONSTRUCTION | 25.64 | 25.64 | 100
6 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Material Requisition To Resource Division |  |  | 181/JD | 21/01/2022 |  | Resource Division | 31.71 | 0 | 0
7 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Material Requisition To Resource Division |  |  | 552/JD | 01/03/2022 |  | Resource Division | 28.13 | 0 | 0
8 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | New Service Connection Charge for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164167, Reference ID : 403024435] |  |  | BP/23-24/71 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
9 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Infrastructure Cost for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084431, Reference ID : 860276011] |  |  | BP/23-24/71 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.71 | 0 | 0
10 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Infrastructure Cost for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084158, Reference ID : 860276008] |  |  | BP/23-24/71 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0
11 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | New Service Connection Charge for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164165, Reference ID : 403024434] |  |  | BP/23-24/71 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
12 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of RAMSAI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 1057/HQ/NMD | 21/06/2024 |  | SUMON ELECTRICAL | 0.73 | 0 | 100
13 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Construction of Boundary wall at H/W Site & 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF RAMSAI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | 187/JD | 21/01/2022 |  | PARESH CHANDRA GUHA | 108.02 | 108.02 | 100
14 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-II) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT - JALPAIGURI. | Assistant Engineer | Junior Engineer | 206/JD | 24/01/2022 |  | ASHIT KUMAR SINGHA | 191.92 | 139.13 | 100
15 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Installation of Iron Elimination Plant (35 m3/hr) including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain...etc at H/W Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | 2268/JD | 21/11/2022 |  | M/S A.B.G. CONSTRUCTION | 29.32 | 29.32 | 100
16 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Material Requisition To Resource Division |  |  | 2217/JD | 01/12/2024 |  | Resource Division | 20.02 | 0 | 0
17 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF RAMSAI (PART-III) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT, JALPAIGURI. | Assistant Engineer | Junior Engineer | 191/JD | 21/01/2022 |  | M/S R.N. TRADERS | 145.02 | 126.62 | 100
18 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-I) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT ¿ JALPAIGURI. | Assistant Engineer | Junior Engineer | 190/JD | 21/01/2022 |  | PARESH CHANDRA GUHA | 197.63 | 189.67 | 100
19 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | 2015/JD | 01/11/2022 |  | M/S R.N. TRADERS | 14.18 | 12.61 | 100
20 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | 140/JD | 17/01/2023 |  | R.S CONSTRUCTION | 14.16 | 12.74 | 60
21 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. | SM/10033 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RAMSAI PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 270/NMD | 21/03/2023 |  | M/S PARITOSH BHOWMICK AND CO. | 20.2 | 18.4 | 100
Total | [12 empty] | 879.23 | 698.74 | 79.47