## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Material Requisition To Resource Division |  |  | 1885/JD | 20/12/2023 |  | Resource Division | 12.09 | 0 | 0
2 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." | Assistant Engineer,HQ | Junior Engineer 2 | 2197/JD | 25/01/2024 |  | SOUMEN GHOSH | 0.44 | 0.39 | 0
3 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | 735/JD | 26/07/2024 |  | PROVA CONSTRUCTION | 103.17 | 0 | 0
4 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.11.2023 to 31.03.2024) | Assistant Engineer,HQ | Junior Engineer | 1601/JD | 08/11/2023 |  | SOMNATH ROY | 0.94 | 0.94 | 100
5 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1421/JD | 20/09/2024 |  | GOURAV CONSTRUCTION CO. | 0.02 | 0 | 90
6 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.04.2024 to 30.08.2024) | Assistant Engineer,HQ | Junior Engineer | 2946/JD | 28/03/2024 |  | SOMNATH ROY | 0.93 | 0.93 | 100
7 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Material Requisition To Resource Division |  |  | 2017/JD | 19/11/2024 |  | Resource Division | 36.79 | 0 | 0
8 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 71 B 9430) |  |  | BP-2024-25-226 | 15/07/2024 |  | FILL & SMILE | 0.18 | 0 | 0
9 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 78 3405) |  |  | BP-2024-25-227 | 15/07/2024 |  | FILL & SMILE | 0.18 | 0 | 0
10 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341713, Reference ID : 403171394] |  |  | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.36 | 0 | 0
11 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 71 B 9430) |  |  | BP-2024-25-228 | 15/07/2024 |  | FILL & SMILE | 0.14 | 0 | 0
12 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341706, Reference ID : 403171321] |  |  | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.99 | 0 | 0
13 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 78 3405) |  |  | BP-2024-25-225 | 15/07/2024 |  | FILL & SMILE | 0.23 | 0 | 0
14 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Supply of Fuel (Diesel) of Vehicle No. WB 25 K 9449 for the Month of July 2024. |  |  | BP-2024-25-311 | 20/08/2024 |  | FILL & SMILE | 0.21 | 0 | 0
15 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Supply of different stationary items for office use under Jalpaiguri R.W.S Sub Division, P.H.E Dte. |  |  | BP-2024-25-121 | 05/06/2024 |  | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 0.25 | 0 | 0
16 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Construction of different components of Barapatina Nutanbus Zone-I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 352/JD | 05/06/2023 |  | JAYANTA GHOSH | 379.06 | 139.2 | 70
17 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Barapatina Nutanbus Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 118/JD | 16/01/2025 |  | ALOKE DEY | 18.75 | 0 | 0
18 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 10/NMD | 06/01/2025 |  | SILIGURI VYAPAR PRIVATE LIMITED | 5.57 | 0 | 0
19 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | 485/RWS | 29/05/2025 |  | DEEP CONSTRUCTION | 8.05 | 0 | 0
20 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 1108/NMD | 16/05/2025 |  | WEBEL TECHNOLOGY LIMITED | 11.9 | 0 | 0
21 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer | Junior Engineer | 1735/JD | 31/07/2025 |  | AJIJUL HAQUE | 0.8 | 0 | 100
22 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | 2001/JD | 25/09/2025 |  | AJIJUL HAQUE | 0.8 | 0 | 50
23 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME | SM/15971 | New | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer | Junior Engineer | 2404/JD | 19/11/2025 |  | AJIJUL HAQUE | 0.4 | 0 | 0
Total | [12 empty] | 600.24 | 141.46 | 23.57