## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Thorough repair and overhauling of the IEP reparing Pump House and other ancillary work at Dabgram Central zone at Dabgram -II G.P. under Dabgram piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | 795/JD | 24/07/2023 |  | NARENDRA KUMAR | 6.8 | 0 | 0
2 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (North Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | 1552/JD | 01/11/2023 |  | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 414.28 | 0 | 0
3 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Material Requisition To Resource Division |  |  | 1827/JD | 14/12/2023 |  | Resource Division | 121.48 | 0 | 0
4 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Material Requisition To Resource Division |  |  | 1104/JD | 24/08/2023 |  | Resource Division | 184.96 | 0 | 0
5 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Retrofittings works including Functional House Hold Tap connection under JJM for Dabgram Water Supply Scheme ( Central Zone ) under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | 796/JD | 24/07/2023 |  | NARENDRA KUMAR | 36.22 | 0 | 100
6 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DABGRAM-II (CENTRAL ZONE,SOUTH ZONE,NORTH ZONE) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1513/NMD | 24/08/2023 |  | ALPHA ENTERPRISE | 143.91 | 0 | 50
7 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of September 2024. |  |  | BP-2024-25-496 | 07/10/2024 |  | FILL & SMILE | 0.22 | 0 | 0
8 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of August 2024. |  |  | BP-2024-25-552 | 17/12/2024 |  | FILL & SMILE | 0.09 | 0 | 0
9 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VII, under SUBHASPALLY CCC APPLICATION NO. 4003412903 Reference ID : 403221491 |  |  | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.6 | 0 | 0
10 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412861 Reference ID : 403221492 |  |  | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0
11 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 71 B 8742 for the Month of July 2024. |  |  | BP-2024-25-341 | 30/08/2024 |  | FILL & SMILE | 0.21 | 0 | 0
12 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of September 2024. |  |  | BP-2024-25-550 | 17/12/2024 |  | FILL & SMILE | 0.21 | 0 | 0
13 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE , T/W-V , Bhoot Para, Thakur Nagar, Behind GC Tiles under SUBHASPALLY CCC APPLICATION NO. 4003511149 , Reference ID : 403289730 |  |  | BP/24-25/240 | 30/10/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.61 | 0 | 0
14 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412817 Reference ID : 403221494 |  |  | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.57 | 0 | 0
15 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of August 2024. |  |  | BP-2024-25-368 | 13/09/2024 |  | FILL & SMILE | 0.22 | 0 | 0
16 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-IV, under SUBHASPALLY CCC APPLICATION NO. 4003412749 Reference ID : 403221493 |  |  | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.23 | 0 | 0
17 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of October 2024. |  |  | BP-2024-25-548 | 17/12/2024 |  | FILL & SMILE | 0.15 | 0 | 0
18 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Different stationary for office under Jalpaiguri Division, PHE Dte. |  |  | BP-2024-25-84 | 17/05/2024 |  | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0
19 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of October 2024. |  |  | BP-2024-25-551 | 17/12/2024 |  | FILL & SMILE | 0.13 | 0 | 0
20 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (Central Zone) i.e. TW, Pump Houses, Water Distribution Network, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block, Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | 936/JD | 08/08/2023 |  | MAA MANASA VYAPAAR | 708.57 | 0 | 43
21 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (South Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | 1708/JD | 04/12/2023 |  | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 526.38 | 0 | 45
22 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/08/2024 to 09/02/2025) | Assistant Engineer,HQ | Junior Engineer 2 | 963/JD | 09/08/2024 |  | RABINDRA NATH DUTTA | 0.88 | 0 | 0
23 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.07.2024 to 13.01.2025) | Assistant Engineer,HQ | Junior Engineer 2 | 649/JD | 11/07/2024 |  | RAKESH SARKAR | 0.88 | 0 | 0
24 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | 271/JD | 07/02/2025 |  | SAPTASWA SARKAR | 4.58 | 0 | 100
25 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2024 to 31.05.2025)". | Assistant Engineer,HQ | Junior Engineer 2 | 2201/JD | 30/11/2024 |  | RUPA PRASAD | 0.88 | 0 | 0
26 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer 2 | 04/HQ/JD | 13/01/2025 |  | RAKESH SARKAR | 0.23 | 0 | 0
27 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 01/04/2025 to 30/04/2025) | Assistant Engineer,HQ | Junior Engineer 2 | 107-HQ/JD | 28/03/2025 |  | RABINDRA NATH DUTTA | 0.15 | 0 | 0
28 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation Order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer 2 | 212/JD | 29/01/2025 |  | SOUMEN GHOSH | 0.88 | 0 | 0
29 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/02/2025 to 31/03/2025) | Assistant Engineer,HQ | Junior Engineer 2 | 41/HQ/JD | 09/02/2025 |  | RABINDRA NATH DUTTA | 0.25 | 0 | 0
30 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer 2 | 70/HQ/JD | 28/02/2025 |  | RAKESH SARKAR | 0.15 | 0 | 0
31 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte.(For the period from01/05/2025 to 30/06/2025) | Assistant Engineer,HQ |  | 817/JD | 30/04/2025 |  | BISWANATH GHOSH | 0.8 | 0 | 0
32 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer 2 | 818/JD | 30/04/2025 |  | PRADIP SAHA | 0.8 | 0 | 0
33 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Material Requisition To Resource Division |  |  | 511/JD | 13/03/2025 |  | Resource Division | 14.82 | 0 | 0
34 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) & Mobil Oil of Vehicle No. WB 71 B 1578 for the Month of December 2024. |  |  | BP-2024-25-746 | 29/03/2025 |  | FILL & SMILE | 0.25 | 0 | 0
35 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of March 2025. |  |  |  | 06/06/2025 |  | FILL & SMILE | 0.25 | 0 | 0
36 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of November 2024. |  |  | BP-2024-25-601 | 10/02/2025 |  | FILL & SMILE | 0.23 | 0 | 0
37 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel Bill for the Month of November,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. |  |  | BP-2024-25-582 | 14/01/2025 |  | FILL & SMILE | 0.27 | 0 | 0
38 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of January 2025. |  |  | BP-2024-25-677 | 27/03/2025 |  | FILL & SMILE | 0.25 | 0 | 0
39 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of November 2024. |  |  | BP-2024-25-573 | 14/01/2025 |  | FILL & SMILE | 0.22 | 0 | 0
40 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of December 2024. |  |  | BP-2024-25-603 | 10/02/2025 |  | FILL & SMILE | 0.21 | 0 | 0
41 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Bill for the Professional Services rendered on Account of Preparation & Submission of e-TDS Return of Form 24Q4, 24Q4 (Revised) & Form 16 & 26Q4, 26Q4 (Revised) & Form 16A for the F.Y. 2023-24 & Form 24Q1 & 26Q1 for the F.Y. 2024-25 & Form 16A. |  |  | BP-2024-25-617 | 19/03/2025 |  | SUSHIL KUMAR SINGHA | 0.22 | 0 | 0
42 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel Bill for the Month of October,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. |  |  | BP-2024-25-583 | 14/01/2025 |  | FILL & SMILE | 0.19 | 0 | 0
43 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of February 2025. |  |  |  | 04/04/2025 |  | FILL & SMILE | 0.21 | 0 | 0
44 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Bill for the Professional Services rendered on Account of Preparation & Submission of GST-Return for the month of Feb¿24 to July¿24 & GSTR-7A Certificate for the month of Feb¿24 to July¿24 & previous months updated GSTR-7A |  |  | BP-2024-25-681 | 27/03/2025 |  | SUSHIL KUMAR SINGHA | 0.25 | 0 | 0
45 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of April 2025. |  |  |  | 09/06/2025 |  | FILL & SMILE | 0.25 | 0 | 0
46 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of February 2025. |  |  |  | 04/04/2025 |  | FILL & SMILE | 0.25 | 0 | 0
47 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of January 2025. |  |  | BP-2024-25-676 | 27/03/2025 |  | FILL & SMILE | 0.23 | 0 | 0
48 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Bill for the Professional Services rendered on Account of Preparation & Submission of e-TDS Return of Form 24Q4, 24Q4 (Revised) & Form 16 & 26Q4, 26Q4 (Revised) & Form 16A for the F.Y. 2023-24 & Form 24Q1 & 26Q1 for the F.Y. 2024-25 & Form 16A. |  |  | BP-2024-25-723 | 27/03/2025 |  | SUSHIL KUMAR SINGHA | 0.1 | 0 | 0
49 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME | SM/18283 | Augmentation | Deposit amount for construction of boundary pillar, Net present value of the Forest (NPV) and Cost of Raising CA Plantation for 100 nos seedling. regarding Ref- Proposal No. FPiV/B/WATER/47 177912024 |  |  |  | 21/05/2025 |  | DIVISIONAL FOREST OFFICER, BAIKUNTHAPUR DIVISION | 7.62 | 0 | 0
Total | [12 empty] | 2209.23 | 0 | 0