## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC MARICH BARI |  |  | BP-2021-22-150 | 17/08/2021 |  | ANIMESH DHAR CHOUDHURY | 3.2 | 0 | 0
2 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing house connection of drinking water to the house hold of command area under Uttar Fulkardabri PWSS under Cooch Behar Division, PHED Dte under Jaldhara Programme |  |  |  | 22/03/2021 |  | MANABENDRA DE | 5.01 | 0 | 0
3 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing house connection of drinking water to the house hold of command area under uttar Fulkardabri PWSS under Cooch Behar Division, PHED Dte under Jaldhara Programme |  |  |  | 16/07/2021 |  | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 5.01 | 0 | 0
4 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in UTTAR FULKARDABRI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | 333/MTB | 04/01/2022 |  | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 5 | 0 | 1
5 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing FHTC and Laying of Pipe line at UTTAR FULKADABRI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | 1463/CD | 10/03/2022 |  | SHIBA ENTERPRISE | 5.37 | 0 | 1
6 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | cost of meterial |  |  | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0 | 0 | 0
7 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | COST PIPES |  |  | BP-2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.73 | 0 | 0
8 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | BP_2021_22_447 | 11/03/2022 |  | PINAKI SAHA | 3.22 | 0 | 0
9 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | BP_2021_22_432 | 10/03/2022 |  | GOUTAM KUMAR DAS | 5.01 | 0 | 0
10 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.35 | 0 | 0
11 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | fhtc |  |  | BP-2021-22-421 | 11/03/2022 |  | MS BIDYUT SARKAR | 12.14 | 0 | 0
12 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FGHTC |  |  | BP-2021_22_462 | 16/03/2022 |  | TAPAN CHANDA | 0.38 | 0 | 0
13 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | BP-2021-22-400 | 17/02/2022 |  | M/S. NITYAGOPAL BANIK | 28.17 | 0 | 0
14 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Material Requisition To Resource Division |  |  | 1105/CD | 27/01/2022 |  | Resource Division | 29.6 | 0 | 0
15 | COOCHBEHAR | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for UTTAR FULKARDABRI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | 142/CD | 06/07/2021 |  | SHIBA ENTERPRISE | 30.31 | 30.31 | 0
Total | [12 empty] | 138.51 | 30.31 | 21.88