## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-424 | 10/03/2022 |  | NORTHE BENGAL CONST CO | 4.98 | 0 | 0
2 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_493 | 31/03/2022 |  | BISWAJIT GUHA | 4.93 | 0 | 0
3 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_503 | 31/03/2022 |  | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 10.52 | 0 | 0
4 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY OF DELIVERY S VALVE DAUWAGURI |  |  | BP-22-23-148 | 26/07/2022 |  | MS BIDYUT SARKAR | 4.82 | 0 | 0
5 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY AND DELIVETY OF JC CUPLING DAWAGURI |  |  | BP-22-23-151 | 26/07/2022 |  | MS BIDYUT SARKAR | 2.48 | 0 | 0
6 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_496 | 31/03/2022 |  | GOUTAM KUMAR DAS | 5.06 | 0 | 0
7 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_495 | 31/03/2022 |  | MATARA CONSTRUCTION CO. | 10.53 | 0 | 0
8 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_492 | 31/03/2022 |  | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 12.17 | 0 | 0
9 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | PIPE |  |  | BP_2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.69 | 0 | 0
10 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-428 | 11/03/2022 |  | KAJAL KUMAR DE | 0.19 | 0 | 0
11 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-427 | 10/03/2022 |  | PINAKI SAHA | 4.93 | 0 | 0
12 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-423 | 10/03/2022 |  | SWAPAN KUMAR ROY | 23.85 | 0 | 0
13 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-425 | 10/03/2022 |  | SHREE RANI SATI ENTERPRISE | 9.96 | 0 | 0
14 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_491 | 30/03/2022 |  | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 10.53 | 0 | 0
15 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | BP-2021-22-422 | 11/03/2022 |  | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 47.38 | 0 | 0
16 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | BP_2021_22_490 | 30/03/2022 |  | SWAPAN KUMAR ROY | 8.6 | 0 | 0
17 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Laying of pipe line with related works at dawaguri W/S Scheme in connection with JJM Programme. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 533/SD | 12/12/2022 |  | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 0.95 | 0 | 1
18 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC AT PWSS |  |  | BP-611-22-23-P | 10/01/2023 |  | KAJAL KUMAR DE | 1.28 | 0 | 0
19 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAWAGURI (AUG) PH NO I |  |  |  | 22/05/2023 |  | WBSEDCL | 1.05 | 0 | 0
20 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT dawaguri (aug) PH NO-I |  |  | BP-2023-24-142 | 01/06/2023 |  | WBSEDCL | 1.05 | 0 | 0
21 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY DIFFT. TYPE OF CHEMICAL FO ALL LABORATORY |  |  | BP-94 | 06/05/2023 |  | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 2.4 | 0 | 0
22 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-B) under JJM. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1352/CD | 19/12/2022 |  | SWAPAN KR.SARKAR | 0.92 | 0 | 100
23 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Providing FHTC Sinking 250mm X 200mm Big dia Tubewell (PART ¿C) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 909/CD | 24/12/2021 |  | GHOSH AND SAHA CONSTRUCTION | 11.48 | 0 | 1
24 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Providing FHTC Boundary Wall SSPost with soak pit & New HDPE Pipe line and other allied works (PART ¿B) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 910/CD | 24/12/2021 |  | PARITOSH PANDIT | 30.61 | 0 | 1
25 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Dowaguri 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1566/CD | 23/03/2022 |  | GHOSH AND SAHA CONSTRUCTION | 2.78 | 0 | 1
26 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Soil investigation work for proposed Over head reservoir of Dawaguri PWSS Scheme under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 500/SD | 25/01/2022 |  | CME CONSTRUCTION | 1.23 | 0 | 100
27 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 401/CD | 23/05/2023 |  | RAHAMAN ENTERPRISE | 9.86 | 0 | 95
28 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Name of Work: Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1026/CD | 22/09/2023 |  | RAHAMAN ENTERPRISE | 10.65 | 0 | 84
29 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Constructions of retaining wall & concrete rd to widen the existing damaged rd runs to HWS from NH 31 at DAWAGURI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1631/CD | 29/03/2022 |  | MS BIDYUT SARKAR | 14.79 | 0 | 0
30 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1337/CD | 24/11/2023 |  | MS BIDYUT SARKAR | 33.07 | 0 | 49
31 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | HIRING VEHICLE FOR AE/TFG |  |  | BP-208 | 31/07/2024 |  | MATRI ENTERPRISEES | 0.01 | 0 | 0
32 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Sitai PWSS UNDER JAL JEEVAN MISSION. |  |  | xxxx/CD | 26/05/2025 |  | M/S J C ENTERPRISE | 6.79 | 0 | 0
33 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dauaguri T.W No I under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | 2872/NMD-II | 17/10/2023 |  | M/S PALI DEB ENGINEERING | 10.51 | 0 | 80
34 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS (within DAUAGURI area) RELATED TO RAJPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | 92/CD | 17/01/2025 |  | KRISHNA GOPAL BASAK | 10.69 | 0 | 0
35 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Construction of 200 cum OHR Providing FHTC & New UPVC/DI Pipe line & other allied works (PART ¿A) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 959/CD | 31/12/2021 |  | MS BIDYUT SARKAR | 50.39 | 0 | 90
36 | COOCHBEHAR | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS (within DAUAGURI area) RELATED TO RAJPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 91/CD | 17/01/2025 |  | SOMENATH MUKHERJEE | 10.68 | 0 | 100
Total | [12 empty] | 373.82 | 0 | 0