## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Adabari water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD |  |  | 2420/NMD-II | 10/08/2023 |  | SUBODH KUMAR BANIK | 21.45 | 0 | 0
2 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Material Requisition To Resource Division |  |  | 142/CD | 27/04/2023 |  | Resource Division | 28.05 | 0 | 0
3 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Execution of different works related to CHHOTO GAROLJHORA PWSS under JAL JEEVAN MISSION |  |  | 284/CD | 09/02/2024 |  | S.G ENTERPRISE | 38.53 | 0 | 0
4 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BARA ADABARI Sathbhandari PWSS UNDER JAL JEEVAN MISSION. |  |  | 2259/CD | 23/12/2024 |  | SWAPAN KR.SARKAR | 10.99 | 0 | 0
5 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARA ADABARI TW NO. I |  |  | BP-2023-24-580 | 01/02/2024 |  | WBSEDCL | 4.37 | 0 | 0
6 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARA ADABARI TW II. |  |  | BP-2023-24-662 | 04/03/2024 |  | WBSEDCL | 5.13 | 0 | 0
7 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Execution of different works related to BARA ADABARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1176/1-5/NBC-1; Dt.: 24-02-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | 1819/CD | 06/03/2023 |  | S.G ENTERPRISE | 392.44 | 0 | 60
8 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | 1264/CD | 02/07/2024 |  | MACKINTOSH BURN LIMITED | 50 | 0 | 20
9 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | 1156/NMD-II | 19/05/2025 |  | WEBEL TECHNOLOGY LIMITED | 11.9 | 0 | 0
10 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS under JAL JEEVAN MISSION |  |  | 701/CD | 17/05/2025 |  | UMEX POLYMERS PVT LTD | 39.68 | 0 | 0
11 | COOCHBEHAR | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Solarization of grid connected pumping installation at Different PWSS at Sitai,Mathabanga and Mekhliganj Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | 1335/NMD-II | 18/06/2025 |  | M R S ELECTRICAL | 5.46 | 0 | 0
Total | [12 empty] | 608.01 | 0 | 0