## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Material Requisition To Resource Division |  |  | 170/CD | 27/04/2023 |  | Resource Division | 31.38 | 0 | 0
2 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Preparation of DPR for Augmentation of Bara Atiabari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | 1017/CD/W | 10/01/2022 |  | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.6 | 3.6 | 100
3 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | New service connection at Bara atiabari PWSS, P/H-III |  |  | BP-2023-24-491 | 21/12/2023 |  | WBSEDCL | 4.41 | 0 | 0
4 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to B.ATIABARI P.KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 304/CD | 09/02/2024 |  | MS SSB CONSTRUCTION CO | 88.79 | 83.14 | 45
5 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 1302/CD | 06/06/2024 |  | MS SSB CONSTRUCTION CO | 86.73 | 85.59 | 30
6 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO BARA ATIABARI PRATHAM KHANDA & PANISALA PWSS UNDER JAL JEEVAN MISSION. |  |  | 2247/CD | 23/12/2024 |  | ABHIJIT KUMAR DAS | 27.19 | 0 | 0
7 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Execution of different works related to BARA ATIABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | 663/CD | 14/07/2023 |  | MS SSB CONSTRUCTION CO | 652.47 | 535.59 | 60
8 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Material Requisition To Resource Division |  |  | 70/CD | 15/01/2025 |  | Resource Division | 30.8 | 0 | 0
9 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of Bara Atiabari Pratham Khanda water supply scheme, TW no I of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | 2444/NMD-II | 11/08/2023 |  | GEETA CONSTRUCTION | 27.85 | 22.13 | 60
10 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED (WITHIN REJ BARA ATIABARI PRATHAM KHANDA and REJ SATKURA AREA) TO Nigamnagar PWSS UNDER JAL JEEVAN MISSION. Part-A |  |  | 644/CD | 05/05/2025 |  | TAPAN CHANDA | 16.04 | 0 | 0
11 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED (WITHIN DUAI SUAI, BARA ATIABARI PRATHAM KHANDA and PUTIMARI BAKSIBAS AREA) TO GAJENDRAPUR AND PRAN MAJUMDAR PWSS UNDER JAL JEEVAN MISSION. |  |  | 597/CD | 28/04/2025 |  | SHRI ANNAPURNA DISTRIBUTORS | 10.55 | 0 | 0
12 | COOCHBEHAR | Coochbehar Division | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/18299 | Augmentation | Charges for new service connection at Rejuvenation of of Bara atiabari pratham khanda PWSS, P/H-IV in the dist of Coochbehar |  |  |  | 09/01/2025 |  | WBSEDCL | 12.96 | 0 | 0
Total | [12 empty] | 992.77 | 730.05 | 73.54