## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Material Requisition To Resource Division |  |  | 2187/RD/PHE | 12/12/2022 |  | Resource Division | 48.12 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Material Requisition To Resource Division |  |  | 579/RD/PHE | 24/02/2023 |  | Resource Division | 47.6 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Laying of Balance Pipeline with ancillary works for ALIGANJ Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | 3554/RD/PHE | 05/12/2024 |  | KARTICK BISWAS | 37.13 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ALIGANJ Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | 590/RD/PHE | 05/03/2024 |  | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 22.52 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Implementation of ALIGANJ and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | 298/RD/PHE | 01/02/2023 |  | UTTAM SAHA | 707.12 | 0 | 65
6 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Aliganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013513) | Assistant Engineer - I | Junior Engineer-02 | 2213/MLMD | 18/07/2023 |  | M/S D.G.B. ENTERPRISE. | 27.21 | 0 | 65
7 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month. | Assistant Engineer ISD |  | 95/RD/PHE | 08/01/2025 |  | M/S GHOSH AND CO. | 0.4 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Quotation for new service connection at ALIGANJ PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12090). |  |  | BP-2024-25-639 | 06/02/2025 |  | W.B.S.E.D.C.LTD | 5.97 | 0 | 0
Total | [12 empty] | 896.07 | 0 | 0