## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Work of Allied pipe Line for FHTC work under Anantapur Zone1 PWSS at Jamundanga and Balapukur mouza at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Department. |  | Junior Engineer Kushmandi | 494/RWS | 05/10/2021 |  | M/S. ANWESHA ENTERPRISE | 2.65 | 0 | 1
2 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Anantapur Zone 2 Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer Kushmandi | 2333/BD | 07/10/2021 |  | CHOUDHURY CONSTRUCTION | 15.86 | 15.86 | 1
3 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Supply of CI / DI specials for Rising Main Interconnection pipe line for Anantapur Zone - I & II piped water supply scheme at Kushmandi Block in the District of Dakshin Dinajpur Under Balurgaht Division P.H.E. Dte. |  | Junior Engineer Kushmandi | 417/RWS | 27/08/2021 |  | THE NEW LOKNATH CONSTRUCTION | 1.06 | 1.06 | 1
4 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantpur Zone 1 Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 504/BD dated :- 25/02/2021 & Tender No. 06 of 2021-2022] |  |  |  | 21/07/2022 |  | DIPESH BHOWMIK | 11.5 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Material Requisition To Resource Division |  |  | 2966/BD | 31/12/2021 |  | Resource Division | 2.2 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Material Requisition To Resource Division |  |  | 204/BD | 02/02/2022 |  | Resource Division | 5.49 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantapur Zone I Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  | Junior Engineer Kushmandi | 509/BD | 25/02/2021 |  | M/S. ANWESHA ENTERPRISE | 21.9 | 0 | 1
Total | [12 empty] | 60.66 | 16.92 | 27.89