## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II, making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Kismatdapat Trimohini (Zone- I) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011528) | Assistant Engineer - I | Junior Engineer-01 | 1137/MLMD | 26/06/2023 |  | MANIK CHANDRA SAHA. | 23.34 | 13.86 | 59
2 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II & III, making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Kismatdapat Trimohini (Zone- II) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011528) | Assistant Engineer - I | Junior Engineer-01 | 2661/MLMD | 10/08/2023 |  | GHOSH BROTHERS... | 46.8 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Kismat Dapat Trimohini,Zone-II, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | 4003286546 | 17/12/2023 |  | W.B.S.E.D.C.LTD | 4.38 | 4.38 | 100
4 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Material Requisition To Resource Division |  |  | 3487/BD | 03/03/2023 |  | Resource Division | 114.92 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Material Requisition To Resource Division |  |  | 575/BD | 19/06/2023 |  | Resource Division | 6.47 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Material Requisition To Resource Division |  |  | 837/BD | 14/07/2023 |  | Resource Division | 9.52 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Sinking of 02 nos 300 mm dia X 200mm dia 81.00 mtr depth Rig Bored Tubewell for Augmentation of KD Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | 92/BD | 24/01/2024 |  | M/S. SARKAR ENTERPRISE | 15.87 | 15.87 | 100
8 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Material Requisition To Resource Division |  |  | 875/BD | 03/05/2024 |  | Resource Division | 25.7 | 0 | 0
9 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Restoration of Trimohini Dhanhati Maniko Road from chainage 2.50 KM TO 5.50 KM under K. D. Trimohini PWSS at Hili Block, Dakshin Dinajpur. |  |  | BP-2024-25-196 | 27/11/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 9.17 | 0 | 0
10 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Restoration of Teor - Binsira-Maniko- Bangalipur Road from chainage 5 KM TO 7.5 KM Km under K. D. Trimohini PWSS at Hili Block, Dakshin Dinajpur. |  |  | BP-2024-25-131 | 12/09/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.57 | 0 | 0
11 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Laying distribution pipe line for augmentation of K.D. Trimohini Pipe Water Supply Scheme(Zone-II) at Hili Dev. Block in the district of Dakhin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | 2703/BD | 21/12/2022 |  | J.D.J. ENTERPRISE | 659.64 | 160.45 | 18
12 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Laying of Rising Main, Providing FHTC, Repairing of 300 Cum capacity OHR with 20m Staging Height, Repairing of Pump House & Blower Room, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of K.D. Trimohini Zone-I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | 3819/BD | 23/03/2023 |  | VENUS CONSTRUCTION | 119.41 | 32.27 | 45
13 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Sinking of Tubewell, Laying of Rising Main, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of K.D. Trimohini Zone-II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer Hili | 1094/BD | 10/08/2023 |  | MINATI CONSTRUCTION | 446.32 | 40.43 | 12
14 | DAKSHIN DINAJPUR | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | Augmentation | Laying distribution pipe line for augmentation of K.D. Trimohini pipe Water Supply Scheme(Zone-I) at Hili Dev. Block in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | 2702/BD | 21/12/2022 |  | M/S. JAN MAHAMMAD | 356.38 | 279.44 | 78
Total | [12 empty] | 1852.51 | 546.7 | 29.51