## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara, Habitation-Ajeiulla Biswas Para) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | 1158/MAAD | 13/06/2022 |  | A. K. CONSTRUCTION | 4.58 | 4.58 | 1
2 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of 20mm dia HDPE pipe at Chaspara, Bara Sujapur Mouzas for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | 1828/MAAD | 27/09/2022 |  | A. K. CONSTRUCTION | 6.25 | 6.24 | 1
3 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Chota Sujapur) | Assistant Engineer-II | Junior Engineer-II | 1747/MAAD | 24/11/2021 |  | A. K. CONSTRUCTION | 44.63 | 44.63 | 1
4 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying UPVC Pipe line at Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | 68/MAAD | 21/01/2022 |  | A. K. CONSTRUCTION | 4.77 | 4.77 | 100
5 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of 90mm dia UPVC Pipe at Bishu More, Bokatola and near Naimouza Subhania High Madrasah under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | 71/MAAD | 21/01/2022 |  | A. K. CONSTRUCTION | 4.79 | 4.79 | 100
6 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of different dia uPVC Pipe at Ajijullah Biswas Para, Makul Biswas Para near Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | 389/MAAD | 08/03/2022 |  | A. K. CONSTRUCTION | 14.46 | 14.46 | 1
7 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | 823/MAAD | 28/04/2022 |  | SUBHASH CHANDRA KESHARI | 37.86 | 37.86 | 100
8 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of 90mm & 160mm dia distribution Pipeline from Firanchak to Muriwali Para for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | 821/MAAD | 27/04/2023 |  | S & G CONSTRUCTION | 14.69 | 14.69 | 100
9 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of distribution Pipe line at Bokatola, Chaspara, Brahmotra for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-II | Junior Engineer-II | 955/MAAD | 11/05/2022 |  | A. K. CONSTRUCTION | 4.76 | 4.76 | 100
10 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Material Requisition To Resource Division |  |  | 1336/MAAD | 18/07/2022 |  | Resource Division | 12.3 | 0 | 0
11 | MALDAH | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | SM/09655 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | 1524/MAAD | 14/08/2023 |  | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 837.46 | 0 | 30
Total | [12 empty] | 986.54 | 136.77 | 13.86