## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Material Requisition To Resource Division |  |  | 721/MD | 25/03/2022 |  | Resource Division | 65.74 | 0 | 0
2 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Harishchandrapur & Boroi GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | 90/MD | 17/01/2023 |  | MAMATA USHA ENTERPRISE | 178.19 | 178.19 | 97
3 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Rashidabad & Kushida GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | 817/MD | 20/02/2023 |  | NEOGI ENTERPRISE | 130.98 | 100.48 | 95
4 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Tulshihata GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | 198/MD | 19/01/2023 |  | MILLENNIUM ENTERPRISR | 97.04 | 82.33 | 100
5 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. | SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Mahendrapur & Bhingole GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | 43/MD | 16/01/2023 |  | MILLENNIUM ENTERPRISR | 97.04 | 84.3 | 100
Total | [12 empty] | 568.98 | 445.3 | 78.26