## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | 3004467221 | 17/10/2023 |  | W.B.S.E.D.C.LTD | 4.05 | 4.05 | 100
2 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | 3004467207 | 17/10/2023 |  | W.B.S.E.D.C.LTD | 4 | 4 | 100
3 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Material Requisition To Resource Division |  |  | 1811/MD | 27/04/2023 |  | Resource Division | 21.65 | 0 | 0
4 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Material Requisition To Resource Division |  |  | 241/MD | 10/01/2024 |  | Resource Division | 4.53 | 0 | 0
5 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Formal work order for Implementation of Uttar Mahinagar Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 1252/MD | 22/03/2023 |  | M/S DAS CONSTRUCTION | 239.41 | 132.61 | 70
6 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Construction of Boundary Wall at Head Work site of Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 3226/MD | 28/06/2024 |  | M/S DAS CONSTRUCTION | 36.14 | 0 | 40
7 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Uttar Mahinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-05,Junior Engineer-06,Junior Engineer-07 | 2943/MLMD | 11/09/2024 |  | M/S SAJAHAN CHOWDHURY | 25.3 | 0 | 80
8 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 3211/MD | 27/06/2024 |  | M/S DAS CONSTRUCTION | 33.31 | 0 | 20
9 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Road cutting and road restoration at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 6207/MD | 09/12/2024 |  | M/S DAS CONSTRUCTION | 5.06 | 0 | 0
10 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme | SM/12765 | New | Providing Balance Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 2891/MD | 17/06/2025 |  | M/S AMIT KUMAR GUPTA | 20.61 | 0 | 0
Total | [12 empty] | 394.06 | 140.66 | 35.7