## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | 659/MD | 22/03/2022 |  | ECO CARE | 3.71 | 3.71 | 1
2 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Material Requisition To Resource Division |  |  | 1811/MD | 27/04/2023 |  | Resource Division | 120.24 | 0 | 0
3 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 1 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | 652/MD | 08/02/2024 |  | J. M. CONSTRUCTION | 4.76 | 0 | 0
4 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of Boundary Wall at 3rd Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | 2969/MD | 10/06/2024 |  | M/S A. B. CONSTRUCTION | 7.13 | 0 | 0
5 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of Boundary Wall at 4th Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prasanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | 3955/MD | 07/08/2024 |  | MAHA MAYA CONSTRUCTION | 7.12 | 0 | 0
6 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | New service connection at pukuria PWSS T/W NO Iv Under EE/MLMD PHE DTE DIST. Malda.( paranpur c c c) |  |  | BP-2024-25-523 | 26/09/2024 |  | W.B.S.E.D.C.LTD | 4.96 | 0 | null
7 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | New service connection at PUKURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Paranpur c c c) |  |  | BP-2024-25-524 | 26/09/2024 |  | W.B.S.E.D.C.LTD | 4.77 | 0 | null
8 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 2 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | 651/MD | 08/02/2024 |  | CHAKRABORTY & MANDAL ENTERPRISE | 4.76 | 0 | 100
9 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Formal work order for the work of Augmentation of PUKHURIA Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | 2022/MD | 18/05/2023 |  | DUTTA ENTERPRISE | 957.93 | 129.15 | 60
10 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Name of Work: Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II,III & IV and making compound lighting arrangement at Head worksite of Pukuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011879) | Assistant Engineer - II | Junior Engineer-05 | 2580/MLMD | 04/08/2023 |  | DEY ENTERPRISE.. | 44.39 | 0 | 91
11 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Material Requisition To Resource Division |  |  | 1039/MD | 18/03/2025 |  | Resource Division | 24.64 | 0 | 0
12 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme | SM/14100 | New | Erection of Property board related to Jal Jeevan Mission works of Paharpur, Sultanpur, Pukuria PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | 661/MD | 19/02/2025 |  | PRITAM ENTERPRISE | 0.73 | 0 | 0
Total | [12 empty] | 1185.13 | 132.86 | 11.21