## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | 51/JSD | 25/01/2022 |  | IMAGIN | 4.16 | 0 | 0
2 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | 52/JSD | 25/01/2022 |  | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
3 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Allied work for Rising main connection to OHR & AIRP in connection with FHTC work of Village of JAGTAI(Village Code-313979) under JAGTAI Water Supply Scheme (Scheme ID- 0005184165) under Jangipur Sub Division,P.H.E. Dte | ASSISTANT ENGINEER |  | 235/JSD | 05/05/2022 |  | MAA CONSTRUCTION | 3.84 | 3.84 | 0
4 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Allied work of laying of HDPE Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village JAGTAI (Village Code-313979)"( Bara Masjid Para) under command area of Jagtai Ground Water based Water supply scheme for Arsenic Affected Areas of Suti-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184165) in the district of Murshidabad. | ASSISTANT ENGINEER |  | 241/JSD | 05/05/2022 |  | MONDAL CONSTRUCTION | 4.7 | 4.7 | 0
5 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna Jal Jeevan Mission and under command area of village of JAGTAI (Village code 313979) under JAGTAI Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184165 | ASSISTANT ENGINEER |  | 4023/MURD | 24/12/2021 |  | HOQUEDAR ALI | 91.45 | 91.45 | 1
6 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | EXTENSION OF PIPELINE AT AURANGABAD PHE SUB CENTRE & JAGTAI SUB CENTRE UNDER SUTI -II BLOCK | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | 228/JSD | 15/01/2020 |  | SUJIT CHOWDHURY | 1.94 | 1.94 | 100
7 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  |  | 14/12/2023 |  | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 23.36 | 0 | 0
8 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | 441-MSD/2023-24 | 15/12/2023 |  | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 23.36 | 0 | 0
9 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | Retrofitting | Laying of HDPE pipeline and FHTC of 191 nos. household for retrofitting works in Jagtai Ground water-based w/s scheme for arsenic affected areas of Suti-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme ID- 0005184165) | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | 1935/MURD | 18/07/2023 |  | HOQUEDAR ALI | 39.92 | 39.92 | 100
Total | [12 empty] | 196.89 | 141.85 | 72.04