## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Material Requisition To Resource Division |  |  | 61/BD-1/2 | 27/04/2023 |  | Resource Division | 29.7 | 0 | 0
2 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | LOCHANPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer |  | 1175/BD-I | 25/07/2024 |  | DEBJIT DAS | 21.57 | 0 | 0
3 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Lochanpur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | 1125/BD-I | 11/07/2024 |  | KHANDAKAR CONSTRUCTION | 8.19 | 0 | 0
4 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | NEW SERVICE CONNECTION AT LOCHANPUR Z1 PH 1 ID 304268981 |  |  |  | 26/11/2024 |  | WBSEDCL | 16.76 | 0 | 0
5 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Lochanpur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | 1131/MEDB | 13/05/2025 |  | HARA PROSAD DAS | 39.97 | 0 | 0
6 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Augmentation of Lochanpur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar -I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | 696/BD-I | 11/08/2023 |  | ARABINDA GHOSH | 323.45 | 69.64 | 10
7 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | 2235/CDD | 11/03/2024 |  | JHARGRAM SPV PRIVATE LIMITED | 20.43 | 14.37 | 20
8 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer |  | 950/BD-I | 18/07/2025 |  | HARBAUER INDIA (P) LTD. | 106.79 | 0 | 0
9 | MURSHIDABAD | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer-I | JE_Pravin Kumar Gupta | 1762/BD-I | 24/03/2023 |  | M/S SOBHA & CO | 2.6 | 2.6 | 100
Total | [12 empty] | 569.45 | 86.61 | 15.21