## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte¿(Sl. No.7) | AE | JE3 | 278/BHM | 09/02/2022 |  | APORUPA CONSTRUCTION | 63.34 | 63.34 | 100
2 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.8) | AE | JE3 | 281/BHM | 09/02/2022 |  | BIJOY KUMAR CHOUDHURY | 52.83 | 43.55 | 95
3 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Connection of distribution pipeline at node 6-40, rising main at MDMC main canal crossing node 147-148 & construction of sluice valve chambers & all other allied works at different locations under Maldanga Piped Water Supply Scheme of Birbhum Division, P.H.E. Dte.(Sl. No.1) | AE(HQ) | JE3 | 2031/BHM | 09/12/2021 |  | ARPAN PANDIT | 1.34 | 0 | 100
4 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Surveying, Planning etc. including obtaining permission on behalf of PHE Dte Supply, Laying & Pushing of 600 mm dia. 10 mm thick M.S Spiral Welded Casing Pipe by of Fe 410 grade as per IS: 3589-2001 Adopting Trenchless Technologies (Jack Pushing Method) under in between NH road crossing for 200 mm dia. Distribution Line at Joypur More (Node Point 25) under Maldanga W/S Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE(HQ) |  | 524/BHM | 11/03/2022 |  | MANASH GHOSH | 2.75 | 0 | 50
5 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Supply & delivery of sluice valve for Maldanga Zone-I W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE(HQ) |  | 419/BHM | 24/02/2022 |  | BIJOY KUMAR CHOUDHURY | 0.13 | 0 | 100
6 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for balance Household from existing distribution system within the command area of Maldanga under Maldanga Water Supply Scheme within Birbhum Division, PHE Dte. | AE(HQ) | Estimator | 1452/BHM | 07/07/2022 |  | APORUPA CONSTRUCTION | 113.81 | 50 | 100
7 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Withdrawing & restroration of 100 mm & 200 mm dia distribution & rising main pipe line at bridge crossing near Maldanga village & providing FHTC for the village of Moulpur, Bhututa & chatrama to declre "SAJAL GRAM" of Maldanga piped water supply scheme under Birbhum division P.H.E Dte. | AE(HQ) | Estimator | 1172/BHM | 11/04/2023 |  | SOURAV MONDAL | 0.97 | 0.97 | 100
Total | [12 empty] | 235.17 | 157.86 | 67.13