## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bikandi, Saora in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.5) | AE | JE2 | 141/BHM | 05/02/2021 |  | QUAZI SIRAJUL ISLAM. | 34.7 | 69.4 | 100
2 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dharampur in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.7) | AE | JE2 | 143/BHM | 05/02/2021 |  | G. B. CONSTRUCTION AND CO. | 40.86 | 40.86 | 100
3 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area in the villages kadya raghunathpur in Raghunathpur WS Scheme (Sl.No.06) |  |  |  | 19/03/2021 |  | M/S MD AMINUL ISLAM | 26.68 | 0 | 0
4 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system with the command areain the villages bilkandi saora in Raghunathpur WS Scheme (Sl.No.05) |  |  |  | 18/03/2021 |  | QUAZI SIRAJUL ISLAM. | 34.7 | 0 | 0
5 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) |  |  |  | 16/03/2021 |  | S R ENTERPRISE | 25.48 | 0 | 0
6 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Inter connection between 2 nos. replacement tube wells to CWR at Raghunathpur Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE2 | 411/AE/NSD | 07/09/2022 |  | BISWAJIT RABIDAS | 0.6 | 0 | 0
7 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kadya, Raghunathpur in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.6) | AE | JE2 | 142/BHM | 05/02/2021 |  | M/S MD AMINUL ISLAM | 36.49 | 72.98 | 100
8 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE2 | 78/BHM | 27/01/2021 |  | S R ENTERPRISE | 5.48 | 10.95 | 50
9 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raghunathpur w/s Scheme (Left out House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.10) | AE | JE2 | 1507/BHM | 09/09/2021 |  | M/S MD AMINUL ISLAM | 74.5 | 37.25 | 100
10 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Miyapur, Barla, Thengapara, Bagbari raghunathpur habitation and adjacent area under Raghunathpur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | 607/AE/NSD | 26/11/2021 |  | ENAMUL ISLAM | 4.82 | 4.82 | 100
11 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Laying distribution system From NP-58 towards Dharampur(079) under Raghunathpur PWSS under Nalhati Sub Division PHED. | AE | JE2 | 277/A/AE/NSD | 16/04/2021 |  | SUNIL RABI DAS | 0.16 | 0 | 0
12 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Laying distribution system From NP-135 towards NP-136 under Raghunathpur PWSS under Nalhati Sub Division PHED. | AE | JE2 | 277/B/AE/NSD | 16/04/2021 |  | SUNIL RABI DAS | 0.16 | 0 | 0
13 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 16.06.2021 to 15.09.2021) of Raghunathpur Water Supply Scheme. | AE | JE1,JE2 | 318/AE/NSD | 15/06/2021 |  | SHIB GANGA CONSTRUCTION | 0.12 | 0 | 0
14 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Continuation work order for Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.03.2022 to 17.06.2022) of Raghunathpur Water Supply Scheme. | AE | JE1,JE2 | 157/NSD | 17/03/2022 |  | SHIB GANGA CONSTRUCTION | 0.12 | 0 | 0
15 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Balance estimate for construction of boundary wall near C.W.R Site including M.S. Ornamental grill railing at Raghunathpur Water Supply Scheme under Nalhati Sub Division P.H.E. Dte. | AE | JE2 | 589/AE/NSD | 22/11/2021 |  | BHARAT CONSTRUCTION | 0.47 | 0 | 100
16 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Sinking of replacement the tubewell of 200mm dia & 60 m. deep with PVC pipe and fibre glass Strainer at Raghunathpur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE2 | 209/AE/NSD | 05/04/2022 |  | MD AMINUL ISLAM | 0.62 | 0 | 100
17 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Work Order for Construction of boundary wall near OHR site at Raghunathpur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (Sl. No.1) | AE | JE2 | 1119/BHM | 09/09/2020 |  | MD. SHAHA JAMAL | 0.82 | 0 | 100
18 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Extension of 63 & 75 mm Dia. UPVC Pipe line in Miapur,Barla,Bagbari & Barmaroi habitations for providing FHTC within Raghunathpur Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. | AE | JE2 | 226/NSD | 19/04/2022 |  | ENAMUL ISLAM | 3.59 | 3.59 | 100
19 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Continuation Work Order for Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.06.2022 to 17.09.2022) of Raghunathpur Water Supply Scheme. | AE | JE1,JE2 | 314/AE/NSD | 17/06/2022 |  | SHIB GANGA CONSTRUCTION | 0.12 | 0 | 100
20 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte | SM/07533 | Retrofitting | Collection of Household Data Through Mobile APP/Hardcopy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Kaitha W/S Scheme under Birbhum Division. | AE | JE2 | 138/BH | 19/08/2021 |  | ENAMUL ISLAM | 0.16 | 0.32 | 0
Total | [12 empty] | 290.64 | 240.18 | 82.64