## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | 2033/BHM | 09/12/2021 |  | TAPAN KUMAR DATTA | 94.18 | 0 | 0
2 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-5) | AE | JE | 1019/BHM | 17/06/2021 |  | SUNIL RABI DAS | 99.56 | 99.56 | 100
3 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat - II Block under Brbhum Division, PHE Dte. (Sl. No.04) | AE | JE | 36 / BH | 26/02/2021 |  | BIJOY KUMAR CHOWDHURY | 4.84 | 9.67 | 100
4 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 179/BH | 03/11/2021 |  | BIJOY KUMAR CHOUDHURY | 3.72 | 0 | 100
5 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | 2033/ BHM | 09/12/2021 |  | TAPAN KUMAR DATTA | 26.91 | 0 | 40
6 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Sashtitalapara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 178/BH | 03/11/2021 |  | M/S K.S. GHOSH | 3.61 | 3.61 | 100
7 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 180/BH | 03/11/2021 |  | MUKADDUMUL MOULA | 3.85 | 0 | 100
8 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 177/BH | 03/11/2021 |  | TAPAN ENTERPRISE | 4.83 | 0 | 50
9 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Konaipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 34/BH | 26/02/2021 |  | MUKADDUMUL MOULA | 4.84 | 9.67 | 0
10 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Sashtitalapara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 37/BH | 26/02/2021 |  | M/S K.S. GHOSH | 4.84 | 9.68 | 0
11 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 35/BH | 26/02/2021 |  | M/S S.N CONSTRUCTION | 4.84 | 9.67 | 0
12 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Baroipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | 38/BH | 26/02/2021 |  | TAPAN ENTERPRISE | 4.84 | 9.67 | 0
Total | [12 empty] | 260.85 | 151.55 | 58.1