## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Providing Electro-mechanical accessories and others for ASENGA and Adjoining moujas water supply scheme in Md Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | 2078/BOL.MD. | 21/08/2023 |  | UNIVERSAL ENTERPRISES | 28.8 | 0 | 70
2 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Material Requisition To Resource Division |  |  | 1433/BHM | 25/04/2023 |  | Resource Division | 95.69 | 0 | 0
3 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Different works related to water supply scheme at ASENGA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | Estimator | 1342/BHM | 20/04/2023 |  | M/S GOUTAM DAS | 409.61 | 0 | 65
4 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA P H NO.I WS SCHEME |  |  | BP-23-24-172 | 07/12/2023 |  | WBSEDCL | 6.71 | 0 | 0
5 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA TW-I (OHR SITE) |  |  |  | 14/03/2024 |  | WBSEDCL | 3.22 | 0 | 0
6 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | New Service connection at Asenga WSS, Block- Khoyrasole under Bolpur Mechanical Division, PHE Dte |  |  |  | 13/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0
7 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA PH NO.2 WS SCHEME |  |  | BP-23-24-171 | 07/12/2023 |  | WBSEDCL | 3.82 | 0 | 0
8 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Jack pushing for crossing PWD Road at different locations including all other allied works for Asenga piped Water Supply Scheme (Md.Bazar Development Block) under Birbhum Division P.H.E. Dte. | AE(HQ) | Estimator,JE | 863/BHM | 26/03/2025 |  | M/S GOUTAM DAS | 65.5 | 0 | 40
Total | [12 empty] | 616.57 | 0 | 0