## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Material Requisition To Resource Division |  |  | 1627/BHM | 28/04/2023 |  | Resource Division | 35.82 | 0 | 0
2 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation for Bolpur SD Hospital & Bolpur water supply scheme under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | 3794/BOL.MD | 12/09/2024 |  | EVEREST INFRATECH INC | 6.77 | 0 | 0
3 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | 305/BSD | 12/08/2022 |  | APEX ENGINEERING | 1.14 | 1.14 | 100
4 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | AE | JE3 | 266/BSD | 11/07/2022 |  | APEX ENGINEERING | 4.11 | 4.11 | 100
5 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Quotation for new service connection at Punna PWSS P/H- I under Ahmedpur CCC |  |  | BP-24-25-281 | 17/12/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
6 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | 1415/CDD | 21/09/2023 |  | JHARGRAM SPV PRIVATE LIMITED | 88.3 | 26.24 | 11
7 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Different works related to water supply scheme at PUNNA PIPED WATER SUPPLY SCHEME(TSM/016169) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | 3668/BHM | 28/08/2023 |  | TEKNO ENTERPRISE | 729.3 | 54.8 | 20
8 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Punna PWSS (TW No II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | 338/BOL.MD | 19/02/2025 |  | SUNIL RABIDAS | 37.24 | 0 | 100
9 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Changing of defective sluice valve/butterfly valve on emergency basis at Gayanananda OHR site of Bolpur Projects under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | 3793/BOL.MD | 12/09/2024 |  | S.K.ELECTRICALS | 4.77 | 0 | 100
Total | [12 empty] | 912.2 | 86.28 | 9.46