## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Material Requisition To Resource Division |  |  | 1116/BHM | 10/04/2023 |  | Resource Division | 9.43 | 0 | 0
2 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Material Requisition To Resource Division |  |  | 971/BHM | 27/03/2023 |  | Resource Division | 363.95 | 0 | 0
3 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Extension of distribution pipe line from Kushmasol to Chandpur, Nichupara and English Medium School and all other allied works for augmentation of Patharchapuri Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. | AE | JE | 671/BHM | 20/02/2024 |  | SOURAV MONDAL | 5.12 | 5.12 | 100
4 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Supply and Delivery of Sub-Mersible Pumping Machineries & others for Augmentation of Patharchapuri PWSS, (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | 3786/BOL.MD | 12/09/2024 |  | DEY ENTERPRISE | 50.29 | 0 | 100
5 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Patharchapri & its adjoining mouzas water supply scheme within Suri - I Block under Birbhum Division PHE Dte | AE | JE | 4143/BHM | 19/10/2023 |  | M/S GOUTAM DAS | 513.52 | 177.52 | 71
6 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Extension of distribution pipe line from Kushmasol to Chandpur, Nichupara and English Medium School and all other allied works for augmentation of Patharchapuri Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. | AE | JE,JE1 | 176/BSSD | 13/03/2025 |  | AMIT KUMAR ROY | 4.82 | 0 | 100
7 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Extension of distribution pipe line from Datababa Mazar and English Medium School and other allied works for augmentation of Patharchapuri Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. |  |  | 400/BSSD | 23/07/2025 |  | SOURAV MONDAL | 5.23 | 0 | 0
8 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Supply & installation of High Lift Pumping Machinery for (Zone - I & II) with other Electro-Mechanical accessories at Augmentation of Pathar Chapri Piped Water Supply Scheme, Block-Suri - I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | 2247/Bol.MD | 13/09/2023 |  | S.K.ELECTRICALS | 29.26 | 16.06 | 100
9 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. | SM/18366 | Augmentation | Quotation for new service connection at Augmentation of Patharchapri (Zone - I & II) H/L PWSS (Mouza- Ranpur) at Block- Suri-I |  |  | BP-24-25-322 | 31/01/2025 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.26 | 0 | 0
Total | [12 empty] | 987.88 | 198.69 | 20.11