## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SONARUDRA Piped Water Supply Scheme at Purbasthali-I Block under Burdwan Division, PHE Dte.(Agreement No. 51/2020-2021 OF SE/CC/PHE. DTE.) | AE(HQs) | J.E. 2 BURDWAN | 4900/BWD | 07/12/2020 |  | J.D.J. ENTERPRISE | 88.29 | 44.19 | 0
2 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Interconnection of tube well no.-1 & Tube well No.-2 along with connection of existing OHR by 100 mm dia DI (K9) pipe and construction of sluice valve chamber of Sonarudra water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 8/KSD | 05/01/2021 |  | BISWAS ENTERPRISE | 2.28 | 4.57 | 1
3 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 1260/KSD Dt-22.12.2021 | 22/12/2021 |  | BABUL SK | 2.42 | 0 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 29/KSD | 07/01/2022 |  | BABUL SK | 0.92 | 0 | 1
5 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | AE(HQs) | J.E. 2 BURDWAN | 3590/BWD | 13/07/2021 |  | PREMANANDA ROY BISWAS | 42.32 | 84.65 | 1
6 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Construction of pathway & plinth protection of Pump House and Surface Drain at the Head Work Site of Sonarudra water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) |  |  | 1218/KSD Dt-10.12.2021 | 10/12/2021 |  | BABUL SK | 1.72 | 0 | 1
7 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | 4318/BWD | 04/11/2020 |  | MD HASIN | 1.02 | 0 | 1
8 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashira Piped Water Supply Scheme at Chanak (Part), Gopalbera, Krishnapur, Gatistha & Kashira (Part) Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. (Agreement No. 99/SE/CC/PHE/Dte of 2020-2021) | AE(HQs) | J.E. 2 BURDWAN | 915/BWD | 02/02/2021 |  | MAJUMDER ENTERPRISE | 7.18 | 14.36 | 0
9 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | SM/06771 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paranpur village and Paranpur habitation of Jahannagar piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-814/BWD/2020-21) | Assistant Engineer |  | 4110/BWD | 16/10/2020 |  | J. K. CORPORATION | 2.74 | 5.49 | 0
Total | [12 empty] | 148.9 | 153.25 | 102.92