## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-2] (Sl No-2) | Assistant Engineer |  | 729/KTS | 16/11/2021 |  | HAMID SK | 1.93 | 1.93 | 1
2 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-1] (Sl No-1) | Assistant Engineer |  | 728/KTS | 16/11/2021 |  | HAMID SK | 1.96 | 1.96 | 1
3 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Supplying, laying and commissioning of Rising main at pump no. - 1 of Panuhat Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-06] | Assistant Engineer |  | 443/KTS | 27/06/2022 |  | HAMID SK | 2.27 | 2.27 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of PANUHAT and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | 387/BWD | 31/01/2023 |  | SUBODH KUMAR MONDAL | 8.35 | 8.35 | 100
5 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. |  |  | 1118/JJM | 27/02/2023 |  | M/S MUNMUN DEY | 0.24 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of November & December'22. |  |  | 1048/JJM | 07/02/2023 |  | M/S MUNMUN DEY | 0.59 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | 3141/BWD | 20/08/2024 |  | VISHAL CONSTRUCTION CO. | 21.4 | 0 | 50
8 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-B).[Agreement No. 728/BWD OF 2020-2021.] | AE(HQs) | J.E. 2 BURDWAN | 1689/BWD | 24/02/2021 |  | HAMID SK | 35.04 | 35.04 | 0
9 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | 1688/BWD | 24/02/2021 |  | HAMID SK | 19 | 37.99 | 0
10 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | SM/07552 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | 394/KTS | 13/04/2023 |  | SIRCON ENGINEERING SERVICES | 1.24 | 1.24 | 100
Total | [12 empty] | 92.02 | 88.78 | 96.48