## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Route Survey and preparation of DPR for MAJHIGRAM-SINGHOT PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-05] | Assistant Engineer |  | 56/KTS | 25/01/2022 |  | RADIANT | 2.63 | 0 | 1
2 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | 1207/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 57 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for MAJHIGRAM SINGOT water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte. [ G.L to P.L Height= 1.20 Mtr] (Sl No-1) | Assistant Engineer |  | 798/KTS | 10/12/2021 |  | BABUL SK | 2.91 | 0 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | Assistant Engineer |  | 159/KTS | 24/02/2022 |  | BABUL SK | 1.72 | 0 | 1
5 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Majhigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block- Mongalkoat ] | ASSISTANT ENGINEER |  | 1173/CMD | 27/06/2022 |  | MITRA ENTERPRISE | 9.03 | 0 | 1
6 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | 1323/BWD | 08/03/2022 |  | Resource Division | 16 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | 545/BWD | 27/01/2022 |  | Resource Division | 16.58 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | 1553/BWD | 15/03/2022 |  | Resource Division | 0.37 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | 1376/BWD | 09/03/2022 |  | Resource Division | 3.83 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Material Requisition To Resource Division |  |  | 3275/BWD | 29/07/2022 |  | Resource Division | 34.57 | 0 | 0
11 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | SM/09569 | Augmentation | Augmentation of MAJHIGRAM SINGOT Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including repair of pump house at head works & 2ND TW site under Mangalkote Block, District - Purba Bardhaman. | Assistant Engineer | JE, Katwa Sub-Division,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | 1939/BWD | 11/04/2022 |  | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 369.39 | 0 | 85
Total | [12 empty] | 514.03 | 0 | 0