## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Carriage of FTK Box to different BMOH office under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | 308/AE/HQ | 10/06/2024 |  | KHUSI BHAKAT | 0.29 | 0.29 | 100
2 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Hire Charges of Training Car & Carriage of FTK Box to different BMOH offices under Burdwan Division, PHE. Dte. |  | Junior Engineer, Burdwan Division | 1130/AE/HQ | 11/09/2025 |  | KHUSI BHAKAT | 0.52 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Uploading charges of all collected & tested data management to State WQ Dashboard using FTK/H2S vials for FHTCs in Burdwan district related to Water Quality Monitoring & Surveillance Activities under Jal Jeevan Mission. | AE(HQs) | J.E. 1 BURDWAN | 353/AE/HQ | 10/03/2025 |  | ALAKA GHOSH | 4.65 | 0 | 100
4 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Engagement of ASHA as FTK User for Water Quality Monitoring and Surveillance of Rural Drinking Water Supply |  |  | 1260/JJM | 24/01/2025 |  | CHIEF MEDICAL OFFICER OF HEALTH (CMOH) | 50.31 | 0 | 0
Total | [12 empty] | 55.76 | 0.29 | 0.51