## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme. |  |  |  | 24/03/2021 |  | S.S. ENTERPRISE | 44.96 | 0 | 0
2 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme |  |  | 264/PFMS | 08/10/2021 |  | S.S. ENTERPRISE | 35.02 | 0 | 0
3 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | PROVIDING FHTC AT BABLARI DEYANGANJ W/S SCHEME UNDER JAL SWAPNO PROGRAM. |  |  | 89/PPMS | 15/07/2021 |  | S.S. ENTERPRISE | 44.96 | 0 | 0
4 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bablari Dewanganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | 44/ND | 06/01/2021 |  | S.S. ENTERPRISE | 14.72 | 0 | 100
5 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Material Requisition To Resource Division |  |  | 93/ND | 06/01/2022 |  | Resource Division | 7.71 | 0 | 0
6 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Material Requisition To Resource Division |  |  | 792/ND | 18/02/2022 |  | Resource Division | 3.71 | 0 | 0
Total | [12 empty] | 151.07 | 0 | 0