## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07472 | Retrofitting | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | 1072/Kly SD-I | 30/11/2022 |  | SUMAN CHAKRABORTY | 4.89 | 0 | 0
2 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting)" (Part-2) | Assistant Engineer |  | 2028/ND | 12/05/2021 |  | TARUN KUMAR BHATTACHARYA | 21.17 | 21.17 | 0
3 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-3) | Assistant Engineer |  | 2029/ND | 12/05/2021 |  | TARUN KUMAR BHATTACHARYA | 28.21 | 28.21 | 100
4 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-1). | Assistant Engineer |  | 2027/ND | 12/05/2021 |  | TARUN KUMAR BHATTACHARYA | 31.73 | 31.73 | 100
5 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07472 | Retrofitting | Material Requisition To Resource Division |  |  | 787/ND | 18/02/2022 |  | Resource Division | 1.1 | 0 | 0
Total | [12 empty] | 87.1 | 81.11 | 93.12