## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  |  | 12/04/2021 |  | CHANDAN ROY | 14.57 | 0 | 0
2 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | use Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  |  | 12/04/2021 |  | USHA CONSTRUCTION | 20.02 | 0 | 0
3 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-B, RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. |  |  | 68/PPMS | 15/07/2021 |  | USHA CONSTRUCTION | 20.02 | 0 | 0
4 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-A,RETROFITTING UNDER NADIA DIVISION, PHE , DTE. |  |  | 79/PPMS | 15/07/2021 |  | CHANDAN ROY | 14.57 | 0 | 0
5 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | 287/PFMS | 08/10/2021 |  | CHANDAN ROY | 8.5 | 0 | 0
6 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | 289/PFMS | 08/10/2021 |  | SANJIB DEY | 12 | 0 | 0
7 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | 78/PFMS | 15/07/2021 |  | SANJIB DEY | 9.86 | 0 | 0
8 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | 402/ND | 22/01/2021 |  | USHA CONSTRUCTION | 8.48 | 8.48 | 0
9 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | 401/ND | 22/01/2021 |  | CHANDAN ROY | 3.76 | 3.76 | 0
10 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | 403/ND | 22/01/2021 |  | SANJIB DEY | 5.25 | 5.25 | 0
Total | [12 empty] | 117.03 | 17.49 | 14.94