## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D | SM/09092 | Retrofitting | Restoration of impact zone along Swarupganj UBI more to Anandabas road in connection to the work Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha and other W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. Sl.No. 03 | Assistant Engineer |  | 244/KSD | 11/03/2022 |  | PAPAN ROY | 1.02 | 0 | 97
2 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D | SM/09092 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer |  | 7292/ND | 20/12/2021 |  | PAPAN ROY | 23.86 | 0 | 95
3 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D | SM/09092 | Retrofitting | Material Requisition To Resource Division |  |  | 7449/ND | 27/12/2021 |  | Resource Division | 34.46 | 0 | 0
4 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D | SM/09092 | Retrofitting | Material Requisition To Resource Division |  |  | 449/ND | 31/01/2022 |  | Resource Division | 0.81 | 0 | 0
5 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D | SM/09092 | Retrofitting | Material Requisition To Resource Division |  |  | 4269/ND | 29/09/2022 |  | Resource Division | 2.51 | 0 | 0
Total | [12 empty] | 62.66 | 0 | 0