## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Birohi) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer-I | Junior Engineer-II | 465/NAD-I | 10/03/2022 |  | GHOSH CONSTRUCTION | 87.29 | 0 | 100
2 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-X (Subarnapur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No. 15) | Assistant Engineer-I | Junior Engineer-II | 428/NAD-I | 07/03/2022 |  | IJABUL SEKH | 94.63 | 0 | 100
3 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XIII (Digha) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 11) | Assistant Engineer-I | Junior Engineer-II | 427/NAD-I | 07/03/2022 |  | SANJIB DEY | 77.79 | 0 | 100
4 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Birohi Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 3157/NAD-I | 25/11/2022 |  | ONKAR ENTERPRISE | 24.44 | 0 | 100
5 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Subarnapur Zone XI under Surface WS Scheme of Haringhata Chakdah Part under NAD -I PHE Dte (sl.no.07) | Assistant Engineer-I | Junior Engineer-II | 3035 /NAD-I | 09/11/2022 |  | DIVINE | 30.28 | 0 | 100
6 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Repair of 500 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House at Digha Zone-XIII under Surface W/S Scheme of Haringhata-Chakdah Part under NAD-I PHE Dte (Sl.no.06) | Assistant Engineer-I | Junior Engineer-II | 1691/NAD-I | 08/09/2022 |  | CHOWDHURY & CO. | 27.56 | 0 | 100
7 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Augmentation work for Zone-XI (Birohi) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata Zone-X, (Subarnapur), Zone-XI (Birohi) and Zone-XIII (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 38/AE-I/NAD-I | 07/01/2023 |  | J & T ENTERPRISE | 4.83 | 0 | 100
8 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Augmentation work for Zone-X (Subarnapur) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 39/AE-I/NAD-I | 07/01/2023 |  | M/S DIPAK ENTERPRISE | 4.83 | 0 | 100
9 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Jackpushing of Pipeline at Ayeshpur More (Near Petrol Pump) at NH-34 and other allied works under JalJeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI, Birohi under JJM underNadia Arsenic Division-I, PHE Dte. (SL.02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 512 / NAD-I | 10/03/2023 |  | M/S DIPAK ENTERPRISE | 7.83 | 0 | 35
10 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Jackpushing of Pipeline at Birohi More(Underpass) at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI,Birohi under JJM under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 513 /NAD-I | 10/03/2023 |  | M/S DIPAK ENTERPRISE | 66.18 | 0 | 100
11 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part | SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Zone-XIII, (Digha), Part-III at Haringhata Block by augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.22) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-IV | 828/NAD-I | 31/03/2023 |  | NISHITH BANERJEE | 11.23 | 0 | 100
Total | [12 empty] | 436.91 | 0 | 0