## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Beharia, Nabla, Goalpur Zone-I and Goalpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla, Goalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I | Junior Engineer-II | 421/NAD-I | 07/03/2022 |  | CHOWDHURY & CO. | 90.4 | 90.4 | 100
2 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Nabla, Part-IV at Santipur block by retrofitting/augmentation of Ground Water Based PWSS for Nabla W/S scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 1319/NAD-I | 04/08/2022 |  | CHOWDHURY & CO. | 55.69 | 55.69 | 100
3 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Beharia WS Scheme Santipur Block under NAD PHE Dte (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 1831 / NAD-I | 27/09/2022 |  | PALCON | 24.1 | 24.1 | 100
4 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary wall , Toilet, Pathway and other allied work at Goalpur Z-II WAter Supply scheme within Santipur block under Nadia Arsenic Division -I , P.H.E.Dte. ( Sl.no. 01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 219 / AE-I/NAD-I | 02/09/2022 |  | BUDDHADEB MONDAL | 0.97 | 0.97 | 100
5 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 136 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House and AIRP at Nabla W/S Scheme Santipur Block under NAD- I PHE Dte (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 1799 /NAD-I | 26/09/2022 |  | M/S S & P CONSTRUCTION | 15.24 | 15.24 | 100
6 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Goalpur, Zone-I W/S Scheme of Santipur Block under NAD- I, PHE Dte ( Sl.no.18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 1725 / NAD-I | 13/09/2022 |  | MONDAL ENTERPRISE | 11.09 | 11.09 | 100
7 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Nabla W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no. 15) | Assistant Engineer-I | Junior Engineer-I | 3093/NAD-I | 21/11/2022 |  | G S CONSTRUCTION AND CO. | 14.12 | 14.12 | 100
8 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary wall Toilet Pathway and other allied work at Goalpur Zone I WS Scheme within Santipur Block under Nadia Arsenic Division-I, PHE Dte ( Sl.No.02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 1798 / NAD-I | 26/09/2022 |  | N.H. ENTERPRISE | 14.08 | 14.08 | 100
9 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House and AIRP at Goalpur Zone-II under Nadia Arsenic Division -I, P.H.E.DTE. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 3157 / NAD-I | 25/11/2022 |  | DAS CONSTRUCTION | 11.04 | 11.04 | 100
10 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Beharia W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no.16) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 2010 / NAD-I | 19/10/2022 |  | S S CONSUTANCYAND CONSTRUCTION | 13.05 | 13.05 | 100
11 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Augmentation work of laying of UPVC and M.S. pipeline and other allied works at Goalpur mouza under Jal Jeevan Mission (JJM) under Goalpur Zone-II, Part-III at Santipur Block under Ground Water Based PWSS for Goalpur Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. (sl.17) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | 536 / NAD-I | 13/03/2023 |  | CHOWDHURY & CO. | 14.94 | 14.94 | 30
12 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing Drilling Crew and other allied works for construction of TW (250mm x 150mm x 300mtr. depth) by utilising Departmental Machineries for Goalpur WS Scheme (Z-II), Santipur-I Block under Nadia District, CDD,PHE Dte. | Driller In Charge | Junior Engineer | 1452/CDD | 30/11/2022 |  | M/S SAIKAT ENTERPRISE | 10.86 | 10.86 | 0
13 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I | Junior Engineer-II | 1364/NAD-I | 12/05/2023 |  | DEBASISH DEY | 5.49 | 5.49 | 100
14 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Malipota. Phulia Para at Santipur block by retrofitting of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division- I, PHE Dte (Sl.no.12) | Assistant Engineer-I | Junior Engineer-II | 2121/NAD-I | 04/09/2023 |  | CHOWDHURY & CO. | 12.86 | 12.86 | 100
Total | [12 empty] | 293.95 | 293.95 | 100