## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division |  |  | 639/PFMS | 16/03/2022 |  | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.54 | 0 | 0
2 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) |  |  | 158EMD,Dt.06.01.23 | 27/03/2023 |  | ABHISEK ENGINEERING CONCERN | 14.19 | 0 | 100
3 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Material Requisition To Resource Division |  |  | 2162/ND | 18/05/2022 |  | Resource Division | 24.2 | 0 | 0
4 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Material Requisition To Resource Division |  |  | 1018/ND | 03/03/2022 |  | Resource Division | 4.31 | 0 | 0
5 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Material Requisition To Resource Division |  |  | 146/ND | 06/01/2023 |  | Resource Division | 0.76 | 0 | 0
6 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Material Requisition To Resource Division |  |  | 3303/ND | 27/07/2022 |  | Resource Division | 4.82 | 0 | 0
7 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Providing FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Kulgachi to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | 3897/ND | 16/07/2024 |  | MANAJIT BISWAS | 25.71 | 0 | 0
8 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Kulgachi to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | 3153/ND | 15/07/2022 |  | M/S DIPAK ENTERPRISE | 248.87 | 188.58 | 86
9 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer | Junior Engineer 2 | 372/ Kly SD-I | 17/03/2023 |  | HORIZEN | 2.7 | 0 | 10
10 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Kulgachi Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | 5124/ND | 17/11/2023 |  | BUDDHADEV MONDAL | 18.91 | 0 | 100
11 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | SM/10078 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | 1599/ND | 10/04/2023 |  | B.M. ENGINEERING & CONSTRUCTION | 46.69 | 0 | 100
Total | [12 empty] | 394.69 | 188.58 | 47.78