## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA |  |  | 52/PFMS | 22/06/2022 |  | HORIZEN | 2.52 | 0 | 0
2 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | 468/RSD | 26/07/2022 |  | RAJ & ENTERPRISE | 4.8 | 0 | 100
3 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Material Requisition To Resource Division |  |  | 4290/ND | 29/09/2022 |  | Resource Division | 4.99 | 0 | 0
4 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Material Requisition To Resource Division |  |  | 2585/ND | 13/06/2023 |  | Resource Division | 2.92 | 0 | 0
5 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Material Requisition To Resource Division |  |  | 1878/ND | 26/04/2023 |  | Resource Division | 15.87 | 0 | 0
6 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Material Requisition To Resource Division |  |  | 2325/ND | 29/05/2023 |  | Resource Division | 4.99 | 0 | 0
7 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Laying of Rising Main for Dakshinpara Zone-I W/S Scheme under JJM, Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | 877(A)RSD | 20/08/2024 |  | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.61 | 0 | 0
8 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Special repair & renovation of hed work site pump house & allide works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | 463/A/RSD | 22/07/2022 |  | CHAYA ENTERPRISE | 0.89 | 0 | 100
9 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | 467/A/RSD | 26/07/2022 |  | SWARASHI CONSTRUCTION | 1.76 | 0 | 90
10 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | 463/RSD | 22/07/2022 |  | SREE GURU CONSTRUCATION | 0.95 | 0 | 100
11 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | 496/EMDdt.24.01.2023 | 17/03/2023 |  | GLACIER ENGINEERING CO. | 8.5 | 0 | 100
12 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | : providing drilling crew and other allied works for construction of Tube well ( 300mm X200mm X 250 IVltrs. Depth) by utilising Departmental Machineries for Dakshinpara w/s scheme (Z-l' TW-l) , Hanskhali Block under Nadia District, CentraiDrilling Divlsion, P.H.E' Dte (2nd Call) | Assistant Engineer | Junior Engineer | 1051/CDD | 16/08/2023 |  | MENAKA ENTERPRISE | 13.44 | 0 | 100
13 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Replacement of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone -I PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | 4894/ND | 02/11/2023 |  | SHYAMAL SHIL | 34.58 | 0 | 96
14 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone-I to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | 4040/ND | 19/09/2022 |  | SHYAMAL SHIL | 112.12 | 0 | 97
15 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr | Assistant Engineer | Junior Engineer 2 | 133/ND | 09/01/2024 |  | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 1.21 | 0 | 95
16 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Dakshinpara Zone-I Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | 2327/ND | 20/05/2025 |  | T.T ENTERPRISE | 12.24 | 0 | 0
17 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | SM/10569 | Augmentation | Land development of Dakshinpara Zone-I piped water supply scheme Head works site under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | 198/RSD | 06/02/2025 |  | TARUN KUMAR BHATTACHARYA | 7.6 | 0 | 100
Total | [12 empty] | 232 | 0 | 0