## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Material Requisition To Resource Division |  |  | 1961/NAD-I | 18/08/2023 |  | Resource Division | 6.22 | 0 | 0
2 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site for Gayeshpur Zone-I & Gobindapur Zone-I PWSS at Shantipur Block providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for PWSS for Boalia, Nabla, Gayeshpur W/S Schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | 1338/NAD-I | 23/08/2024 |  | B.S. ENTERPRISE | 26.73 | 0 | 65
3 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Construction and installation of Manifold and allied works at OHR site under for Goalpur Zone-I PWSS including augmentation works under Gayeshpur Zone-I PWSS at Shantipur Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-II | 1968/NAD-I | 28/11/2024 |  | M/S DREAM INFRASTRUCTURE | 16.83 | 0 | 0
4 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Laying of UPVC pipeline including providing FHTC at Goalpur and Boalia W/S Scheme, Shnatipur Block under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 05) |  |  | 1566/NAD-I | 26/09/2024 |  | CONSTRUCTURE | 13.85 | 0 | 0
5 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GAYESPUR (Z-I) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | 1606/EMD | 26/04/2023 |  | STANDARD ENGINEERING | 12.22 | 0 | 100
6 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nabla Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Nabla Part-III Piped W/S Scheme (sl.no.21) | Assistant Engineer-I | Junior Engineer-II | 1162 / NAD-I | 28/04/2023 |  | CHOWDHURY & CO. | 13.06 | 0 | 100
7 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Supply & delivery of automatically controlled Diaphragm type Chlorinator at Gayeshpur Zone-I P/H-I W/S Sch for accommodate FHTC work, Under ESMD-II PHE Dte. | Assistant Engineer | Junior Engineer | 752/EMSD-II | 09/10/2023 |  | STANDARD ENGINEERING | 0.9 | 0 | 100
8 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Material Requisition To Resource Division |  |  | 59/NAD-I | 16/01/2024 |  | Resource Division | 4.31 | 0 | 0
9 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-III | 1672 / NAD-I | 07/09/2022 |  | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 34.08 | 0 | 70
10 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Part-III at Santipur Block bY Augmentation of Ground Water Based PWSS for Boalia W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-I, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Boalia Water Supply Scheme within Santipur Block, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-I Water Supply Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-II Water Supply Scheme, Repair of 550 cum capacity Over Head Reservoir and other allied works at Boalia water supply scheme AND Repair of 250 cum capacity Over Head Reservoir and other allied works at Gayeshpur Zone-I water supply scheme underNadia Arsenic Division-I , PHE Dte. (Sl.no. 03) | Assistant Engineer-I | Junior Engineer-II | 1697/NAD-I | 13/07/2023 |  | JAL PRAVHAHIKA PVT. LTD., | 493.44 | 0 | 45
11 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I | Junior Engineer-II | 1899/NAD-I | 14/08/2023 |  | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 27 | 0 | 0
12 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Gayeshpur Zone-I W/S Scheme under Santipur Block of capacity 60 cum/hr. underaugmentation of Gayeshpur Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II | 1900/NAD-I | 14/08/2023 |  | HARBAUER INDIA PRIVATE LIMITED | 134.01 | 0 | 23
13 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | 1079/NAD-I | 15/07/2024 |  | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 99.54 | 0 | 65
14 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Providing Boundary Illumination with allied works at Boalia, Nabla, Gayeshpur Z-1 and Gayeshpur Z II, Part III under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12021) | Assistant Engineer |  | 1169/EMD | 04/06/2025 |  | SWAPAN ENTERPRISE | 17.35 | 0 | 0
15 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Augmentation of Pipeline including FHTC by changing bib cock or stop cock or stand post or washing & refixing ferrule at different areas under Gayespur (Panpara) water supply scheme under Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | 164/NAD-I | 29/04/2025 |  | R R ENTERPRISE | 5.38 | 0 | 0
16 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc | SM/12021 | Augmentation | Augmentation of FHTC by changing bib cock or stop cock or stand post or washing & refixing ferrule at Simulia under Nabla water supply scheme under Santipur Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 02) | Assistant Engineer-I | Junior Engineer-II | 349/AE-I/NAD-I | 26/12/2024 |  | MONDAL ENTERPRISE | 0.66 | 0 | 100
Total | [12 empty] | 905.58 | 0 | 0