## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Providing drilling crew and other allied works lbr construction olTube Well (300mm X200rrnr X 250 Mtrs. Depth) by utilising Depanmental Machineries for Fulia Tor'r,nship WiS Scherne (Z- Il, 'l'/W-l),Santipur Block r-rnder Nadia District, Central Drilling Division, P.H E. Dte. | Assistant Engineer | Junior Engineer | 1006/CDD | 09/08/2023 |  | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0
2 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-II) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | 421/RSD | 08/05/2023 |  | HORIZEN | 3.1 | 3.1 | 100
3 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR FULIA TOWNSHIP W/S SCHEME (Z-II, TW-I), SANTIPUR BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | 878/CDD | 11/07/2023 |  | UTTAM KUMAR CHATTERJEE | 15 | 0 | 100
4 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | 5349/ND | 01/12/2023 |  | IMAGIN | 1.97 | 0 | 40
5 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 210 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-II to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | 4314/ND | 06/08/2024 |  | MONDAL PRECISION PRIVATE LIMITED | 394.85 | 0 | 0
6 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II , III, IV , V and VI (New) , Zone-II under Fulia Town Ship ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-18374] | Assistant Engineer |  | 2156/EMD | 30/08/2024 |  | CONCORD EMC ENCLAVE LLP | 75.36 | 0 | 0
7 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-3 site at Fulia Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | 925/RSD | 14/09/2023 |  | HANDICRAFT CONSTRUCTION | 4.2 | 0 | 100
8 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-4 site at Fulia Zone-II Water supply scheme under Ranaghat Sub - Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | 926/RSD | 14/09/2023 |  | B K ENGINEERING | 4.26 | 0 | 100
9 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Fencing with R.C.C. pillar (9 nos Govt. Land) at different locations under Fulia Zone- I & II water supply scheme under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | 911/RSD | 13/09/2023 |  | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.17 | 0 | 100
10 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer 2 | 5189/ND | 22/11/2023 |  | MRINAL DASGUPTA | 6.76 | 0 | 100
11 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Badkulla/FULIA TOWNSHIP (Z-II) PWSS W/S Scheme(TW-II) , under Nadia District, Central Drilling Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | 1660/CDD | 17/10/2023 |  | SUNRISE ENGINEERING CORPORATION | 14.41 | 0 | 100
12 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Material Requisition To Resource Division |  |  | 3688/ND | 03/07/2024 |  | Resource Division | 44.99 | 0 | 0
13 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Material Requisition To Resource Division |  |  | 7562/ND | 27/12/2024 |  | Resource Division | 51.02 | 0 | 0
14 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | New power connection charges for FULIA Water Supply scheme Z - II , Pump House No - II |  |  | BP-190-24-25 | 13/12/2024 |  | W.B.S.E.D.C.L (FULIA C.C.C) | 3.52 | 0 | 0
15 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | New power connection charges for FULIA Water supply scheme -II, Pump House No-III |  |  | BP-188-24-25 | 13/12/2024 |  | W.B.S.E.D.C.L (FULIA C.C.C) | 3.46 | 0 | 0
16 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | service connection charges for fulia township |  |  | BP-65-24-25 | 10/07/2024 |  | W.B.S.E.D.C.L (FULIA C.C.C) | 9.54 | 0 | 0
17 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | New Power connection charges for FULIA Water supply scheme Z-II Pump House No- V |  |  | BP-189-24-25 | 13/12/2024 |  | W.B.S.E.D.C.L (FULIA C.C.C) | 3.85 | 0 | 0
18 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z-II, Pump House - IV |  |  | BP-191-24-25 | 13/12/2024 |  | W.B.S.E.D.C.L (FULIA C.C.C) | 7.91 | 0 | 0
19 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials,saddle piece etc. all complete Construction Of 1000 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 1000 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-II to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | 3539/ND | 11/08/2023 |  | AMAL DUTTA ROY | 915.05 | 112.13 | 81
20 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-5 site at Fulia Zone-II Water supply scheme under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | 124/RSD | 29/01/2024 |  | M/S ASIT ROY BHOWMICK | 4.36 | 0 | 100
21 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of 94.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-VI under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer |  | 659/ND | 11/02/2025 |  | SADHANA CONSTRUCTION CO. | 8.07 | 0 | 0
22 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of 49.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-V under Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | 88/RSD | 14/01/2025 |  | M/S KM ENTERPRISE | 5.43 | 0 | 0
23 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of 421.00 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125 mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, H/W under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer |  | 628/ND | 10/02/2025 |  | GOPAL KIRTYANIYA | 33.5 | 0 | 0
24 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-6 site at Fulia Zone-II Water supply scheme under Ranaghat Sub - Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | 927/RSD | 14/09/2023 |  | SREE GURU CONSTRUCATION | 4.2 | 0 | 100
Total | [12 empty] | 1636.87 | 115.24 | 7.04