## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance Cum Work Order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1096/BD | 06/04/2023 |  | MONDAL & CO. (BASIRHAT). | 62.05 | 47.57 | 0
2 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Dk Durgamandop FP School, DTD Sahid Smriti Bidyalaya & Durgamandop Sardar para High School within the command area of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | 1053/HSD | 31/08/2023 |  | M/S RAJPATH CONSTRUCTION. | 0.69 | 0 | 0
3 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | 2401/BD | 17/08/2022 |  | MONDAL & CO. (BASIRHAT). | 266.78 | 266.78 | 1
4 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-02) of EE/EMD of 2022-23 |  |  | 3383 /EMD | 14/08/2022 |  | C.M.S. ENGINEERING CONCERN. | 10.36 | 10.36 | 45
5 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | 1044/HSD | 31/08/2023 |  | ANKUSH CONSTRUCTION & CO. | 0.93 | 0.93 | 100
6 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | 1043/HSD | 31/08/2023 |  | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100
7 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | 2652/BD | 01/09/2023 |  | MONDAL & CO. (BASIRHAT). | 56.73 | 56.73 | 84
8 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | 1415/HSD | 06/11/2023 |  | SARKAR ENTERPRISE | 0.83 | 0 | 100
9 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Material Requisition To Resource Division |  |  | 2471/BD | 24/08/2022 |  | Resource Division | 7.56 | 0 | 0
10 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-01) of EE/EMD of 2022-23 |  |  | 3382EMD | 09/09/2022 |  | BOSE & CHATTERJEE INDUSTRIES | 11.36 | 0 | 70
11 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | 3312/BD | 27/11/2024 |  | SUBHAJIT SAHA | 31.69 | 0 | 0
12 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Durgamandop water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | 276/HSD | 06/03/2024 |  | ANKUSH CONSTRUCTION & CO. | 0.97 | 0 | 83
13 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Durgamandop Mouza within Durgamandop w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 888/HSD | 07/08/2024 |  | SARKAR ENTERPRISE & CO. | 0.93 | 0 | 100
14 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 4182/BD | 30/10/2023 |  | DEBASIS SAMADDAR | 150.76 | 0 | 60
15 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Khosbas mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 258/HSD | 30/01/2025 |  | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.96 | 0 | 100
16 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Installation of CCTV Camera Connection at Pump house no 1 & 2 for Durgamandop w/s scheme, Sandeshkhali -II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | 187/HSD | 28/01/2025 |  | M/S DATTA ENTERPRISE. | 0.58 | 0 | 100
17 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Repairing FHTC with pipeline at Dakshin Durgamandop Das para with laying of 63 mm dia UPVC pipe line in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | 533/HSD | 10/03/2025 |  | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 100
18 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | 110/BD | 09/01/2025 |  | MD.SALIM GAZI. | 5.87 | 0 | 0
19 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Adhikary para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 466/HSD | 28/02/2025 |  | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 100
20 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Ghat para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | 307/HSD | 04/02/2025 |  | SARKAR ENTERPRISE & CO. | 0.98 | 0 | 100
21 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Bairagi para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 338/HSD | 06/02/2025 |  | RATAN SARKAR. | 0.96 | 0 | 100
22 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Ghat para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 247/HSD | 30/01/2025 |  | SARKAR ENTERPRISE & CO. | 0.97 | 0 | 100
23 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Char para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | 256/HSD | 30/01/2025 |  | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 100
24 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Singh para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | 380/HSD | 10/02/2025 |  | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 100
25 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Adhikary para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 246/HSD | 30/01/2025 |  | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 100
26 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Colony para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 182/HSD | 27/01/2025 |  | SARKAR ENTERPRISE & CO. | 0.94 | 0 | 100
27 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap | SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Parul para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | 306/HSD | 04/02/2025 |  | SARKAR ENTERPRISE & CO. | 0.98 | 0 | 100
Total | [12 empty] | 619.59 | 383.28 | 61.86