## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  |  | 06/04/2021 |  | M/S BISWAS CONSTRUCTION | 7.43 | 0 | 0
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  |  | 12/04/2021 |  | GOBINDA MAITY | 3.29 | 0 | 0
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  |  | 19/03/2021 |  | M/S BISWAS CONSTRUCTION | 12 | 0 | 0
4 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  |  | 15/03/2021 |  | GOBINDA MAITY | 16.4 | 0 | 0
5 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | 115/Hug | 19/01/2022 |  | MERCANTILE HALL | 44.14 | 44.14 | 100
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1511/HUG | 22/07/2022 |  | R CONSTRUCTION | 17.48 | 17.48 | 100
7 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Placement of Fund |  |  | 844368 | 19/01/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 0.01 | 0 | 0
8 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main Pipe line in between 3rd T.W By to pass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 111/CH | 10/02/2022 |  | M/S S.G. CONSTRUCTION | 4.18 | 0 | 0
9 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main in between 2nd T.W to O.H.R Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 398/CH | 06/05/2022 |  | M/S S.G. CONSTRUCTION | 2.69 | 0 | 100
10 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main in between 2nd T.W to OHR Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 398/CH | 06/05/2022 |  | M/S S.G. CONSTRUCTION | 2.66 | 2.66 | 100
Total | [12 empty] | 110.27 | 64.27 | 58.28