## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | FHTC |  |  |  | 15/03/2021 |  | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 10.5 | 0 | 0
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | FHTC |  |  |  | 15/03/2021 |  | JAI BHARAT COMMERCIAL CORPORATION | 25 | 0 | 0
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | Providing 130 nos. tap connection at Bagbari mouza, Kanaipur mouza, Nazirpur mouza and sardarpur mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | 15/chan | 05/01/2022 |  | M/S RAJKUMAR KHAN | 10.06 | 10.06 | 100
4 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of MADPUR Water Supply Scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 209/chan | 13/04/2022 |  | M/S RAJKUMAR KHAN | 1.99 | 1.99 | 100
5 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | Providing 132 nos. tap connection at Madpur mouza, Maheshpur mouza, Radhanagar mouza and Nandanbati mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | 221/chan | 13/04/2022 |  | M/S RAJKUMAR KHAN | 5.13 | 5.13 | 100
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | Material Requisition To Resource Division |  |  | 1125/5/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0
7 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | SM/07953 | Retrofitting | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Madpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 727/HUG | 05/03/2024 |  | BAKSHI ENTERPRISE | 9.38 | 9.38 | 100
Total | [12 empty] | 74.38 | 26.56 | 35.71