## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of DUMURDAHA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | 2276/HUG | 19/10/2022 |  | TAPAS ADHYA | 10.75 | 0 | 0
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Hiring of diesel drive motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | 45/CMSD-II(D) | 27/02/2023 |  | SIDDHARTHA CHATTERJEE | 0.9 | 0 | 0
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dadpur, Kamalpur, Sija & Ramnagar Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | 725/Hug | 07/04/2022 |  | DAS ENTERPRISE (SAMIR DAS) | 76.68 | 40.26 | 0
4 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing drilling crew and other allied works for construction of Tube Well (300mmx200mmx150Mtrs) by utilisiling departmental rig machineries for Durmurdaha W/S Scheme, balagarh Block under Hooghly Division, CDD, PHE Dte. | Driller In Charge | Junior Engineer | 62/CDD | 06/04/2023 |  | UNIVERSAL ENTERPRISES | 9.95 | 0 | 100
5 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dumurdaha dham & Aschitpur Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | 724/Hug | 07/04/2022 |  | MS PRADIP KUMAR PAL | 49.54 | 33.8 | 0
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Material Requisition To Resource Division |  |  | 1123/3/HUG | 06/06/2022 |  | Resource Division | 11 | 0 | 0
7 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | 209/CMSD-II(D) | 25/08/2023 |  | SIDDHARTHA CHATTERJEE | 0.94 | 0 | 0
8 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Repairing of Existing O.H.R at H/W site of Dumurdaha Zone- II Water supply scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Balagarh, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | 536/HUG | 20/02/2024 |  | DAS ENTERPRISE (SAMIR DAS) | 8.03 | 0 | 100
Total | [12 empty] | 167.79 | 74.06 | 44.14