## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | SM/11997 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | 2201/HUG | 14/12/2021 |  | SARKAR CONSTRUCTION | 18.07 | 0 | 0
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | SM/11997 | Retrofitting | Providing 1400 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | 1681/HUG | 13/09/2021 |  | BIMAL KUMAR HALDER | 55 | 0 | 0
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | SM/11997 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1130/HUG | 19/04/2023 |  | BAKSHI ENTERPRISE | 17.24 | 0 | 30
Total | [12 empty] | 90.3 | 0 | 0