## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | SM/09479 | Retrofitting | Household survey in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | 88/BSD | 28/01/2022 |  | TAPAS DEY | 0.76 | 0.76 | 0
2 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | SM/09479 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household - 2267 nos. |  | Junior Engineer | 319/BQA | 22/02/2022 |  | JAI BHARAT COMMERCIAL CORPORATION | 121.49 | 121.47 | 100
3 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | SM/09479 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-02( Napra(Part-B) , Bagulia ), Total House Hold -323 |  | Junior Engineer | 858/BQA | 25/02/2021 |  | SARKAR CONSTRUCTION | 27.82 | 0 | 0
4 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | SM/09479 | Retrofitting | Material Requisition To Resource Division |  |  | 450/BQA | 03/03/2022 |  | Resource Division | 12.47 | 0 | 0
5 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surpa Nagar (74), Sonatapal (75), Beliara (76), Malator (77), Bhimpur (94), Santor (95), Tapoban (96), Birsinghapur (97) & Jagannathpur (98) mouzas by retrofitting Aguri Band | SM/09479 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in , Santor (95) & Birsinghapur (97) mouzas by retrofitting Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household -25 |  | Junior Engineer | 801/BQA | 11/04/2023 |  | JAI BHARAT COMMERCIAL CORPORATION | 5.69 | 5.55 | 100
Total | [12 empty] | 168.22 | 127.77 | 75.96