## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Construction Boundary wall at CWR site of Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 3019/BQA | 03/11/2023 |  | SWAPAN KUMAR PATRA | 12.15 | 0 | 0
2 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Material Requisition To Resource Division |  |  | 1120/BQA | 12/05/2023 |  | Resource Division | 91.73 | 0 | 0
3 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Khayerbani piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | 2033/BMD | 01/09/2023 |  | RAJIB COMPANY | 45.28 | 21.8 | 48
4 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Material Requisition To Resource Division |  |  | 116/BQA | 10/01/2024 |  | Resource Division | 4.95 | 0 | 0
5 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA |  |  |  | 28/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
6 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA |  |  | BP-2023-24-177 | 22/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
7 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | SConstruction of 2 Nos. 100 Cum Clear Water Reservoir for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | 2636/BQA | 21/09/2023 |  | SUBHADIP KOLE | 47.49 | 16.71 | 30
8 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | 2866/BQA | 11/10/2023 |  | TAPAS PAL | 38.91 | 0 | 0
9 | BANKURA | Bankura Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | SM/18040 | New | Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Sub-Surface Water Based Khayerbani Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 2867/BQA | 11/10/2023 |  | M/S SUPRIYA CHATTERJEE | 38.91 | 0 | 38
Total | [12 empty] | 284.61 | 38.51 | 13.53