## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Tender No- 204/2022-23 of EE/PD) |  |  | BP-2022-23-258 | 14/09/2022 |  | KOUSHIK CHATTERJEE | 13.82 | 0 | 0
2 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply tap connection arrangement for 3 nos. AWC within Manbazar-II block (Part-I) of Purulia District under Purulia Division, PHE Dte. (Tender No- 206/2022-23 of EE/PD) |  |  | BP-2022-23-265 | 20/09/2022 |  | SOUVIK MANDAL | 17.41 | 0 | 0
3 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | 741/PD | 02/05/2022 |  | SANTANU BANERJEE | 71.2 | 68.06 | 0
4 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within MANBAZAR-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | 1862/PD | 13/12/2022 |  | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 99.14 | 92.48 | 0
5 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 62 nos AWC within Manbazar-II Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | 81/PD | 17/01/2023 |  | RAJAT KARMAKAR | 34.46 | 0 | 0
6 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | 743/PD | 02/05/2022 |  | SOUVIK MANDAL | 17.41 | 0 | 0
7 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Manbazar-II Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | 744/PD | 02/05/2022 |  | KM ENTERPRISES | 22.4 | 22.4 | 0
8 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Manbazar-II Block (Part-O) & 1 no AWC within Manbazar-II Block (Part-Q)of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | 1714/PD | 22/11/2022 |  | M DHARA & BROTHERS | 75.9 | 75.9 | 100
9 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-II Block (Part-C) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | 1712/PD | 22/11/2022 |  | ANUP KUMAR SAHA | 91.07 | 91.07 | 100
10 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-IV)" | Assistant Engineer | Junior Engineer | 1715/PD | 22/11/2022 |  | PRIYATOSH MUKHERJEE | 44.22 | 44.22 | 100
11 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-F), 4 nos AWC within Balarampur Block (Part-E) & 2 nos AWC within Balarampur Block (Part-G) of Purulia District under Purulia Division, PHE Dte.(Phase-IV) | Assistant Engineer |  | 1124/PD | 25/07/2022 |  | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 81.58 | 0 | 69
12 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | 742/PD | 02/05/2022 |  | KOUSHIK CHATTERJEE | 35.04 | 20.67 | 100
13 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 22 nos AWC within Manbazar-II Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1160/PD | 01/08/2022 |  | EQUIPMENTS AND SPARES AGENCIES | 174.15 | 132.38 | 100
14 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Manbazar-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1161/PD | 01/08/2022 |  | EQUIPMENTS AND SPARES AGENCIES | 197.77 | 102.95 | 100
15 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-II Block (Part-K), 2 nos AWC within Manbazar-II Block (Part-L) & 1 nos AWC within Manbazar-II Block (Part-M) & & 1 nos AWC within Manbazar-II Block (Part-N)of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer | Junior Engineer | 1732/PD | 22/11/2022 |  | KM ENTERPRISES | 17.13 | 0 | 100
16 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-II Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer | Junior Engineer | 1713/PD | 22/11/2022 |  | EQUIPMENTS AND SPARES AGENCIES | 86.29 | 18.33 | 85
Total | [12 empty] | 1079 | 668.47 | 61.95