## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Preparation of DPR for Augmentation of Bamunhati PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | 321/AE/USD | 16/08/2022 |  | APEX ENGINEERING | 4.04 | 4.01 | 100
2 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part F :- LDS & FHTC of Southern Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 651/HD | 17/02/2023 |  | M/S MITRA CONSTRUCTION | 35.66 | 0 | 0
3 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part H :- LDS & FHTC of Part II of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 653/HD | 17/02/2023 |  | SUPRIYA MAHANTI MISRA | 22.76 | 0 | 0
4 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No.- I, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 911/ED | 22/02/2023 |  | SAIKAT ENTERPRISE | 11.51 | 0 | 0
5 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part L :- LDS & FHTC of Part VI of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 657/HD | 17/02/2023 |  | BISWAJIT SAMANTA | 15.72 | 0 | 0
6 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Material Requisition To Resource Division |  |  | 1754/HD | 26/04/2023 |  | Resource Division | 120.09 | 0 | 0
7 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Laying Distribution System & Providing House Hold Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part C :- LDS & FHTC of Srirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 2749/HD | 28/07/2023 |  | CREATION CONSTRUCTION | 176.47 | 0 | 0
8 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Renovation of boundary wall at old Headwork Site of Bamunhati W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E.Dte. | AE/Ulu | JE/USD | 3235/AE/USD | 12/03/2024 |  | A.A ENTERPRISE | 3.02 | 3.02 | 100
9 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part O:-LDS & FHTC of Part-IX of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 648/HD | 17/02/2023 |  | JHARNA ENTERPRISE | 11.08 | 0 | 100
10 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part B :- LDS & FHTC of Barbangalpur Village) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | 649/HD | 17/02/2023 |  | S. R. ENTERPRISE | 76.95 | 0 | 60
11 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part I :- LDS & FHTC of Part III of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 654/HD | 17/02/2023 |  | ASHOKE ENGINEERING WORKS | 11.31 | 0 | 0
12 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part E :- LDS & FHTC of Norther Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 650/HD | 17/02/2023 |  | B.M ENTERPRISE | 63.69 | 0 | 0
13 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part Q:- FHTC of Part XI ) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 661/HD | 17/02/2023 |  | SR TRADING CORPORATION | 3.98 | 0 | 0
14 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part G :- LDS & FHTC of Part I of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 652/HD | 17/02/2023 |  | JOY GURU TRADING | 38.68 | 0 | 75
15 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 1195/HD | 23/03/2023 |  | ACME CONSTRUCTION | 38.86 | 36.38 | 85
16 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Laying Distribution System & Providing House Hold Tap Connection (FHTC) & AugmeConstruction of 500cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of Bamunhati Piped Water Supply Scheme (Part A :- Bamunhati Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 1594/HD | 12/04/2023 |  | M/S SRIKANTA PATRA | 219.51 | 0 | 30
17 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Laying Distribution System & Providing Household Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part D :-LDS & FHTC of Mahishrekha Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 2697/HD | 24/07/2023 |  | CONSTRUCTION CORNER | 104.49 | 0 | 60
18 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Bamunhati PWSS (2nd Tube well) of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | 1464/HD | 19/03/2025 |  | NOBLE ENTERPRISE | 5.9 | 0 | 0
19 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Bamunhati PWSS of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | 1207/HD | 04/03/2025 |  | M/S SRIKANTA PATRA | 7.05 | 0 | 0
20 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No. III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | 3465/ED | 11/08/2023 |  | B.T. PROJECT PVT. LTD. | 23.5 | 0 | 0
21 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part J :- LDS & FHTC of Part IV of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 655/HD | 17/02/2023 |  | ABONTICA ENTERPRISE | 27.01 | 0 | 100
22 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part P:- LDS & FHTC of Part X of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 660/HD | 17/02/2023 |  | KALIDAS ENTERPRISE | 3.9 | 0 | 100
23 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part K :- LDS & FHTC of Part V of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 656/HD | 17/02/2023 |  | LOKENATH ENTERPRISES | 12.64 | 0 | 100
24 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part M :- LDS & FHTC of Part VII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 658/HD | 17/02/2023 |  | ARINDAM ENTERPRISE | 20.11 | 0 | 100
25 | HOWRAH | Howrah Division | Augmentation of Bamunhati Water Supply Scheme | SM/12874 | Augmentation | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part N:- LDS & FHTC of Part VIII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | 659/HD | 17/02/2023 |  | S.B ENTERPRISE | 8.73 | 0 | 100
Total | [12 empty] | 1066.68 | 43.42 | 4.07